## Sheet1
Month | Client Name | Project / Workstream Name | CSP | Application / App Team | Deliverable | Work Item / Product Backlog Item | Type (Plan, Design, Dev, QA, Deploy, Document) | Acceptance Criteria | Team Member | Dependencies | Waiting On | Capacity | Sprint | Estimated Start Date | Estimated End Date | Estimated Effort (Hours) | Actual Start Date | Actual End Date | Actual Effort Hours | ETC (Estimate to Complete) | EAC (Estimate at Completion) | Variance | Status (Completed / Pending) | Remarks
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Renters GenAI Docs App | Architecture Review | 480612 | Review | SignOff by CEP leads | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, |  | 80 | 2025 Q1 Sprint1 | 2025-08-01 | 1/13/2025 | 2 | 2025-08-01 | 2025-08-01 | 2 | 0 | 2 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Renters GenAI Docs App | Create App Subscription | 480613 | Deploy | Subscription Creation | Robert | Robert |  |  | 2025 Q1 Sprint1 | 2025-08-01 | 1/13/2025 | 2 | 2025-09-01 | 2025-09-01 | 0 | 0 | 0 | -2 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Renters GenAI Docs App | TFE and Greenfield team Onboarding | 480614 | Deploy | TFE Onboarding | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, |  |  | 2025 Q1 Sprint1 | 2025-08-01 | 1/13/2025 | 2 | 2025-09-01 | 2025-09-01 | 1 | 0 | 1 | -1 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Renters GenAI Docs App | TFC Workspace Creation | 480615 | Deploy | Workspace creation | Pavan/Shad | Shad |  |  | 2025 Q1 Sprint1 | 2025-09-01 | 1/13/2025 | 2 | 2025-09-01 | 2025-09-01 | 1 | 0 | 1 | -1 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Renters GenAI Docs App | Okta groups Creation | 480616 | Deploy | Okta group Creation | Pavan | Okta Team |  |  | 2025 Q1 Sprint1 | 2025-08-01 | 1/13/2025 | 4 | 2025-09-01 | 1/13/2025 | 4 | 0 | 4 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Renters GenAI Docs App | Service Credentials Mapping | 480618 | Deploy | Create SP | Pavan | Robert / Alex / Shiva |  |  | 2025 Q1 Sprint1 | 2025-08-01 | 1/13/2025 | 4 | 2025-09-01 | 1/13/2025 | 4 | 0 | 4 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Renters GenAI Docs App | Resource Group Creation | 480619 | Deploy | Create RG | Pavan | Robert / Alex / Shiva |  |  | 2025 Q1 Sprint1 | 2025-08-01 | 1/13/2025 | 4 | 2025-09-01 | 1/13/2025 | 4 | 0 | 4 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Renters GenAI Docs App | TFC Workspace - RG mapping | 480620 | Deploy | Map Workspace to RG | Pavan | Robert / Alex / Shiva |  |  | 2025 Q1 Sprint1 | 2025-08-01 | 1/13/2025 | 4 | 2025-09-01 | 1/13/2025 | 4 | 0 | 4 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Renters GenAI Docs App | Created Datadog Dashboard | 480621 | Deploy | Datadog Dashboard | Pavan | Robert |  |  | 2025 Q1 Sprint1 | 2025-08-01 | 1/13/2025 | 2 | 2025-09-01 | 1/13/2025 | 2 | 0 | 2 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Renters GenAI Docs App | Add subscription to Logic Monitor | 480622 | Deploy | Logic Monitor Integration | Pavan | Robert |  |  | 2025 Q1 Sprint1 | 2025-08-01 | 1/13/2025 | 2 | 2025-09-01 | 1/13/2025 | 0 | 0 | 0 | -2 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Renters GenAI Docs App | Add subscription to Datadog | 480623 | Deploy | Datadog Integration | Pavan | Robert |  |  | 2025 Q1 Sprint1 | 2025-08-01 | 1/13/2025 | 2 | 2025-09-01 | 1/13/2025 | 2 | 0 | 2 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Renters GenAI Docs App | Update Confluence | 480624 | Deploy | Update Confluence | Pavan |  |  |  | 2025 Q1 Sprint1 | 2025-08-01 | 1/13/2025 | 2 | 2025-09-01 | 1/13/2025 | 1 | 0 | 1 | -1 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Enterprise Analytics Protal | Architecture Review | 481578 | Review | SignOff by CEP leads | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, |  | 80 | 2025 Q1 Sprint2 | 1/13/2025 | 1/17/2025 | 2 | 1/13/2025 | 1/13/2025 | 1 | 0 | 1 | -1 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Enterprise Analytics Protal | Create App Subscription | 481579 | Deploy | Subscription Creation | Robert | Robert |  |  | 2025 Q1 Sprint2 | 1/13/2025 | 1/17/2025 | 2 | 1/13/2025 | 1/21/2025 | 0 | 0 | 0 | -2 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Enterprise Analytics Protal | TFE and Greenfield team Onboarding | 481580 | Deploy | TFE Onboarding | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, |  |  | 2025 Q1 Sprint2 | 1/13/2025 | 1/17/2025 | 2 | 1/13/2025 | 1/21/2025 | 1 | 0 | 1 | -1 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Enterprise Analytics Protal | TFC Workspace Creation | 481581 | Deploy | Workspace creation | Pavan/Shad | Shad |  |  | 2025 Q1 Sprint2 | 1/13/2025 | 1/17/2025 | 2 | 1/13/2025 | 1/21/2025 | 1 | 0 | 1 | -1 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Enterprise Analytics Protal | Okta groups Creation | 481582 | Deploy | Okta group Creation | Pavan | Okta Team |  |  | 2025 Q1 Sprint2 | 1/13/2025 | 1/17/2025 | 4 | 1/13/2025 | 1/21/2025 | 4 | 0 | 4 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Enterprise Analytics Protal | Service Credentials Mapping | 481584 | Deploy | Create SP | Pavan | Robert / Alex / Shiva |  |  | 2025 Q1 Sprint2 | 1/13/2025 | 1/17/2025 | 4 | 1/13/2025 | 1/23/2025 | 4 | 0 | 4 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Enterprise Analytics Protal | Resource Group Creation | 481585 | Deploy | Create RG | Pavan | Robert / Alex / Shiva |  |  | 2025 Q1 Sprint2 | 1/13/2025 | 1/17/2025 | 4 | 1/13/2025 | 1/23/2025 | 4 | 0 | 4 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Enterprise Analytics Protal | TFC Workspace - RG mapping | 481586 | Deploy | Map Workspace to RG | Pavan | Robert / Alex / Shiva |  |  | 2025 Q1 Sprint2 | 1/13/2025 | 1/17/2025 | 4 | 1/13/2025 | 1/23/2025 | 6 | 0 | 6 | 2 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Enterprise Analytics Protal | Created Datadog Dashboard | 481587 | Deploy | Datadog Dashboard | Pavan | Robert |  |  | 2025 Q1 Sprint2 | 1/13/2025 | 1/17/2025 | 2 | 1/13/2025 | 1/23/2025 | 2 | 0 | 2 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Enterprise Analytics Protal | Add subscription to Logic Monitor | 481588 | Deploy | Logic Monitor Integration | Pavan | Robert |  |  | 2025 Q1 Sprint2 | 1/13/2025 | 1/17/2025 | 2 | 1/13/2025 | 1/23/2025 | 0 | 0 | 0 | -2 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Enterprise Analytics Protal | Add subscription to Datadog | 481589 | Deploy | Datadog Integration | Pavan | Robert |  |  | 2025 Q1 Sprint2 | 1/13/2025 | 1/17/2025 | 2 | 1/13/2025 | 1/23/2025 | 2 | 0 | 2 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | Enterprise Analytics Protal | Update Confluence | 481590 | Deploy | Update Confluence | Pavan |  |  |  | 2025 Q1 Sprint2 | 1/13/2025 | 1/17/2025 | 2 | 1/13/2025 | 1/23/2025 | 1 | 0 | 1 | -1 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | LnFNextGen | Architecture Review | 481037 | Review | SignOff by CEP leads | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, |  |  | 2025 Q1 Sprint2 | 1/15/2025 | 1/20/2015 | 2 | 1/15/2025 | 2025-11-01 | 1 | 0 | 1 | -1 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | LnFNextGen | Create App Subscription | 481038 | Deploy | Subscription Creation | Robert | Robert |  |  | 2025 Q1 Sprint2 | 1/15/2025 | 1/20/2015 | 2 | 1/15/2025 | 1/21/2025 | 0 | 0 | 0 | -2 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | LnFNextGen | TFE and Greenfield team Onboarding | 481039 | Deploy | TFE Onboarding | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, |  |  | 2025 Q1 Sprint2 | 1/15/2025 | 1/20/2015 | 2 | 1/15/2025 | 1/21/2025 | 1 | 0 | 1 | -1 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | LnFNextGen | TFC Workspace Creation | 481040 | Deploy | Workspace creation | Pavan/Shad | Shad |  |  | 2025 Q1 Sprint2 | 1/15/2025 | 1/20/2015 | 2 | 1/15/2025 | 1/21/2025 | 1 | 0 | 1 | -1 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | LnFNextGen | Okta groups Creation | 481041 | Deploy | Okta group Creation | Pavan | Okta Team |  |  | 2025 Q1 Sprint2 | 1/15/2025 | 1/20/2015 | 4 | 1/15/2025 | 1/21/2025 | 4 | 0 | 4 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | LnFNextGen | Service Credentials Mapping | 481042 | Deploy | Create SP | Pavan | Robert / Alex / Shiva |  |  | 2025 Q1 Sprint2 | 1/15/2025 | 1/20/2015 | 4 | 1/15/2025 | 1/23/2025 | 4 | 0 | 4 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | LnFNextGen | Resource Group Creation | 481043 | Deploy | Create RG | Pavan | Robert / Alex / Shiva |  |  | 2025 Q1 Sprint2 | 1/15/2025 | 1/20/2015 | 4 | 1/15/2025 | 1/23/2025 | 4 | 0 | 4 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | LnFNextGen | TFC Workspace - RG mapping | 481044 | Deploy | Map Workspace to RG | Pavan | Robert / Alex / Shiva |  |  | 2025 Q1 Sprint2 | 1/15/2025 | 1/20/2015 | 4 | 1/15/2025 | 1/23/2025 | 6 | 0 | 6 | 2 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | LnFNextGen | Created Datadog Dashboard | 481045 | Deploy | Datadog Dashboard | Pavan | Robert |  |  | 2025 Q1 Sprint2 | 1/15/2025 | 1/20/2015 | 2 | 1/15/2025 | 1/23/2025 | 2 | 0 | 2 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | LnFNextGen | Add subscription to Logic Monitor | 481046 | Deploy | Logic Monitor Integration | Pavan | Robert |  |  | 2025 Q1 Sprint2 | 1/15/2025 | 1/20/2015 | 2 | 1/15/2025 | 1/23/2025 | 0 | 0 | 0 | -2 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | LnFNextGen | Add subscription to Datadog | 481047 | Deploy | Datadog Integration | Pavan | Robert |  |  | 2025 Q1 Sprint2 | 1/15/2025 | 1/20/2015 | 2 | 1/15/2025 | 1/23/2025 | 2 | 0 | 2 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Onboarding | Azure | LnFNextGen | Update Confluence | 481048 | Deploy | Update Confluence | Pavan |  |  |  | 2025 Q1 Sprint2 | 1/15/2025 | 1/20/2015 | 2 | 1/15/2025 | 1/23/2025 | 1 | 0 | 1 | -1 | Complete
2025-01-25 | Assurant | CEP Adoption / App Support | AWS | Assurant Labs | EKS - Infoblox Integration | 479906 | Design | EKS - Infoblox Integration | Pavan |  |  |  | 2025 Q1 Sprint1 | 2025-02-01 | 2025-06-01 | 16 | 2025-02-01 | 2025-07-01 | 16 | 0 | 16 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Support | AWS | Assurant Labs | EKS - Infoblox Integration - Documenation | 480267 | Design | Document EKS - Infoblox Integration | Pavan |  |  |  | 2025 Q1 Sprint1 | 2025-06-01 | 1/13/2025 | 12 | 2025-06-01 | 1/13/2025 | 12 | 0 | 12 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Support | AWS | Assurant Labs | ACM Integration with Key Factor | 477342 | Design | ACM Integration with Key Factor | Pavan | Robert / Security Team | Security Team |  | 2025 Q1 Sprint2 | 1/23/2025 | 2/14/2025 | 4 | 1/23/2025 |  | 4 | 0 | 4 | 0 | Complete | Remaining 12 hrs of Work moved to Sprint 3
2025-01-25 | Assurant | CEP Adoption / App Support | AWS | Dojo Portal on AWS | TFC Workspace Creation | 479979 | Deploy | Workspace creation | Pavan/Shad | Shad |  |  | 2025 Q1 Sprint2 | 1/17/2025 | 1/24/2025 | 4 | 1/24/2025 | 1/24/2025 | 4 | 0 | 4 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Support | K8s | DSO Team | Max_pods per node issue | 480769 | Deploy | Identify Cause | Pavan |  |  |  | 2025 Q1 Sprint1 | 2025-07-01 | 2025-08-01 | 8 | 2025-07-01 | 2025-07-01 | 8 | 0 | 8 | 0
2025-01-25 | Assurant | CEP Adoption / App Support | AWS | Observability | Datadog Private Locations patching | 480475 | Deploy | Patch the Datadog privet locations on EKS | Pavan |  |  |  | 2025 Q1 Sprint1 | 2025-06-01 | 2025-06-01 | 8 | 2025-06-01 | 2025-06-01 | 8 | 0 | 8 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Support | AWS | Observability | Create Workspace Principal for Grafana | 480291 | Deploy | Create Workspace Principal | Pavan |  |  |  | 2025 Q1 Sprint1 | 2025-06-01 | 2025-06-01 | 4 | 2025-06-01 | 2025-06-01 | 4 | 0 | 4 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Support | Azure | Enterprise Analytics Protal | EAP: Onboarding Support | 482403 | Deploy | Onboarding Guidence | Pavan |  |  |  | 2025 Q1 Sprint2 | 1/24/2025 | 1/26/2025 | 4 | 1/24/2025 | 1/26/2025 | 4 | 0 | 4 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Support | Azure | DSO Team | [SCTASK1372003] Terraform module does not have parameter "os_disk_type" | 482515 | Deploy | Add feature | Pavan | Robert / Alex |  |  | 2025 Q1 Sprint2 | 1/29/2025 | 2025-05-02 | 16 | 1/29/2025 | 1/30/2025 | 16 | 0 | 16 | 0 | Complete
2025-01-25 | Assurant | CEP Adoption / App Support | Azure | Enterprise Sites Team | Update App Gateway module to validate secret ids used for certificates | 483129 | Deploy | bug Fix | Pavan | Robert / Alex |  |  | 2025 Q1 Sprint2 | 1/31/2025 | 2025-05-02 | 8 | 1/29/2025 | 1/31/2025 | 8 | 0 | 8 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Support | Azure | DSO Team | [SCTASK1377579] Need help with RCA with windows node pool with AKS is not transmitting data to Datadog | 483185 | Deploy | Identify the Root Cause | Pavan |  |  | 80 | 2025 Q1 Sprint3 | 2025-03-02 | 2025-03-02 | 8 | 2025-03-02 | 2025-03-02 | 8 | 0 | 8 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Support | AWS | Assurant Labs | ACM Integration with Key Factor | 477342 | Design | ACM Integration with Key Factor | Pavan | Robert / Security Team | Security Team |  | 2025 Q1 Sprint3 | 1/23/2025 | 2/14/2025 | 12 | 1/23/2025 | 2025-12-02 | 2 | 10 | 12 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Support | Azure | DSO Team | AKS - Add ability to set the upgrade schedule | 482609 | Deploy | Add feature | Pavan | Robert / Alex |  |  | 2025 Q1 Sprint3 | 2025-04-02 | 2025-12-02 | 24 | 2025-04-02 | 2025-12-02 | 16 | 4 | 20 | -4 | Complete
2025-02-25 | Assurant | CEP Adoption / App Support | Azure | DSO Team | Ephemeral Storage config issues | 483860 | Deploy | Feature | Pavan |  |  |  | 2025 Q1 Sprint3 | 2025-06-02 | 2025-06-02 | 8 | 2025-06-02 | 2025-06-02 | 8 | 0 | 8 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Support | Azure | Enterprise Sites Team | Update App Gateway module to validate secret ids used for certificates | 483129 | Deploy | Feature | Pavan |  |  |  | 2025 Q1 Sprint3 | 2025-06-02 | 2025-06-02 | 8 | 2025-06-02 | 2025-06-02 | 8 | 0 | 8 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Support | Azure | DSO Team | Terraform Validation Error | 483861 | Deploy | Identify the Root Cause | Pavan |  |  |  | 2025 Q1 Sprint3 | 2025-10-02 | 2025-10-02 | 4 | 2025-10-02 | 2025-10-02 | 4 | 0 | 4 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Support | AWS | Assurant Labs | ACM Integration with Key Factor | 477342 | Design | ACM Integration with Key Factor | Pavan | Robert / Security Team | Security Team |  | 2025 Q1 Sprint3 | 1/23/2025 | 2/14/2025 | 10 | 1/23/2025 | 2025-10-02 | 6 | 4 | 10 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Support | Azure | DSO Team | AKS - Add ability to set the upgrade schedule | 482609 | Deploy | Add feature | Pavan | Robert / Alex |  | 80 | 2025 Q1 Sprint4 | 2025-04-02 | 2025-12-02 | 8 | 2025-04-02 | 2025-12-02 | 4 | 4 | 8 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / Account Migration | Azure | NA | Prep activities for AWS Migration Plan | 483965 | Deploy | Update Confluence | Pavan |  |  |  | 2025 Q1 Sprint4 | 2025-10-02 | 2025-10-02 | 8 | 2025-10-02 | 2025-10-02 | 8 | 0 | 8 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / Account Migration | Azure | NA | Document Risks and Workaround for AWS Migration | 484028 | Deploy | Update Confluence | Pavan |  |  |  | 2025 Q1 Sprint4 | 2025-10-02 | 2/13/2025 | 12 | 2025-11-02 | 2/14/2025 | 12 | 0 | 12 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | AWS | TMO Max Value DR | Mock Onboarding |  | Deploy | Mock | Pavan |  | TMO Max Value team |  | 2025 Q1 Sprint4 | 2/13/2025 | 2/19/2025 | 20 | 2/13/2025 | 2/19/2025 | 20 | 0 | 20 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | AWS | TMO Max Value DR | Architecture Review | 484230 | Review | SignOff by CEP leads | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, | TMO Max Value team |  | 2025 Q1 Sprint4 | 2025-03-02 | 2025-03-02 | 2 | 2025-03-02 | 2025-03-02 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | AWS | TMO Max Value DR | Create AWS Account | 484231 | Deploy | Subscription Creation | Pavan | Robert | TMO Max Value team |  | 2025 Q1 Sprint4 | 2/13/2025 | 2/19/2025 | 2 | 2/13/2025 | 2/19/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | AWS | TMO Max Value DR | TFE and Greenfield team Onboarding | 484232 | Deploy | TFE Onboarding | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, | TMO Max Value team |  | 2025 Q1 Sprint4 | 2/13/2025 | 2/19/2025 | 2 | 2/13/2025 | 2/19/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | AWS | TMO Max Value DR | TFC Workspace Creation | 484233 | Deploy | Workspace creation | Pavan/Shad | Shad | TMO Max Value team |  | 2025 Q1 Sprint4 | 2/13/2025 | 2/19/2025 | 2 | 2/13/2025 | 2/19/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | AWS | TMO Max Value DR | Okta groups Creation | 484234 | Deploy | Okta group Creation | Pavan | Okta Team | TMO Max Value team |  | 2025 Q1 Sprint4 | 2/13/2025 | 2/19/2025 | 2 | 2/13/2025 | 2/19/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | AWS | TMO Max Value DR | Service Credentials Mapping | 484235 | Deploy | Create SP | Pavan |  | TMO Max Value team |  | 2025 Q1 Sprint4 | 2/13/2025 | 2/19/2025 | 2 | 2/13/2025 | 2/19/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | AWS | TMO Max Value DR | Support Case creation for AZ mapping | 484236 | Deploy | Create AWS Support case | Pavan |  | TMO Max Value team |  | 2025 Q1 Sprint4 | 2/13/2025 | 2/19/2025 | 2 | 2/13/2025 | 2/19/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | AWS | TMO Max Value DR | Created Datadog Dashboard | 484237 | Deploy | Datadog Dashboard | Pavan |  | TMO Max Value team |  | 2025 Q1 Sprint4 | 2/13/2025 | 2/19/2025 | 2 | 2/13/2025 | 2/19/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | AWS | TMO Max Value DR | Add subscription to Logic Monitor | 484238 | Deploy | Logic Monitor Integration | Pavan |  | TMO Max Value team |  | 2025 Q1 Sprint4 | 2/13/2025 | 2/19/2025 | 2 | 2/13/2025 | 2/19/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | AWS | TMO Max Value DR | Add subscription to Datadog | 484239 | Deploy | Datadog Integration | Pavan |  | TMO Max Value team |  | 2025 Q1 Sprint4 | 2/13/2025 | 2/19/2025 | 2 | 2/13/2025 | 2/19/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | AWS | TMO Max Value DR | Update Confluence | 484240 | Deploy | Update Confluence | Pavan |  | TMO Max Value team |  | 2025 Q1 Sprint4 | 2/13/2025 | 2/19/2025 | 2 | 2/13/2025 | 2/19/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | Shipsurance | Architecture Review | 484458 | Review | SignOff by CEP leads | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, | Shipsurance Team |  | 2025 Q1 Sprint4 | 2/19/2025 | 2/24/2025 | 2 | 2/19/2025 | 2/24/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | Shipsurance | Create App Subscription | 484458 | Deploy | Subscription Creation | Robert | Robert | Shipsurance Team |  | 2025 Q1 Sprint4 | 2/19/2025 | 2/24/2025 | 2 | 2/19/2025 | 2/24/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | Shipsurance | TFE and Greenfield team Onboarding | 484459 | Deploy | TFE Onboarding | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, | Shipsurance Team |  | 2025 Q1 Sprint4 | 2/19/2025 | 2/24/2025 | 2 | 2/19/2025 | 2/24/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | Shipsurance | TFC Workspace Creation | 484461 | Deploy | Workspace creation | Pavan/Shad | Shad | Shipsurance Team |  | 2025 Q1 Sprint4 | 2/19/2025 | 2/24/2025 | 2 | 2/19/2025 | 2/24/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | Shipsurance | Okta groups Creation | 484462 | Deploy | Okta group Creation | Pavan | Okta Team | Shipsurance Team |  | 2025 Q1 Sprint4 | 2/19/2025 | 2/24/2025 | 4 | 2/19/2025 | 2/24/2025 | 4 | 0 | 4 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | Shipsurance | Service Credentials Mapping | 484463 | Deploy | Create SP | Pavan | Robert / Alex / Shiva | Shipsurance Team |  | 2025 Q1 Sprint4 | 2/19/2025 | 2/24/2025 | 4 | 2/19/2025 | 2/24/2025 | 4 | 0 | 4 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | Shipsurance | Resource Group Creation | 484464 | Deploy | Create RG | Pavan | Robert / Alex / Shiva | Shipsurance Team |  | 2025 Q1 Sprint4 | 2/19/2025 | 2/24/2025 | 4 | 2/19/2025 | 2/24/2025 | 4 | 0 | 4 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | Shipsurance | TFC Workspace - RG mapping | 484465 | Deploy | Map Workspace to RG | Pavan | Robert / Alex / Shiva | Shipsurance Team |  | 2025 Q1 Sprint4 | 2/19/2025 | 2/24/2025 | 4 | 2/19/2025 | 2/24/2025 | 4 | 0 | 4 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | Shipsurance | Created Datadog Dashboard | 484466 | Deploy | Datadog Dashboard | Pavan | Robert | Shipsurance Team |  | 2025 Q1 Sprint4 | 2/19/2025 | 2/24/2025 | 2 | 2/19/2025 | 2/24/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | Shipsurance | Add subscription to Logic Monitor | 484467 | Deploy | Logic Monitor Integration | Pavan | Robert | Shipsurance Team |  | 2025 Q1 Sprint4 | 2/19/2025 | 2/24/2025 | 2 | 2/19/2025 | 2/24/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | Shipsurance | Add subscription to Datadog | 484468 | Deploy | Datadog Integration | Pavan | Robert | Shipsurance Team |  | 2025 Q1 Sprint4 | 2/19/2025 | 2/24/2025 | 2 | 2/19/2025 | 2/24/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | Shipsurance | Update Confluence | 484469 | Deploy | Update Confluence | Pavan |  | Shipsurance Team |  | 2025 Q1 Sprint4 | 2/19/2025 | 2/24/2025 | 2 | 2/19/2025 | 2/24/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | France Visa T&C Sidekick | Architecture Review | 484517 | Review | SignOff by CEP leads | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, | FVSK Team |  | 2025 Q1 Sprint4 | 2/21/2025 | 2/28/2025 | 2 | 2/21/2025 | 2/28/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | France Visa T&C Sidekick | Create App Subscription | 484518 | Deploy | Subscription Creation | Robert | Robert | FVSK Team |  | 2025 Q1 Sprint4 | 2/21/2025 | 2/28/2025 | 2 | 2/21/2025 | 2/28/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | France Visa T&C Sidekick | TFE and Greenfield team Onboarding | 484520 | Deploy | TFE Onboarding | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, | FVSK Team |  | 2025 Q1 Sprint4 | 2/21/2025 | 2/28/2025 | 2 | 2/21/2025 | 2/28/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | France Visa T&C Sidekick | TFC Workspace Creation | 484521 | Deploy | Workspace creation | Pavan/Shad | Shad | FVSK Team |  | 2025 Q1 Sprint4 | 2/21/2025 | 2/28/2025 | 2 | 2/21/2025 | 2/28/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | France Visa T&C Sidekick | Okta groups Creation | 484522 | Deploy | Okta group Creation | Pavan | Okta Team | FVSK Team |  | 2025 Q1 Sprint4 | 2/21/2025 | 2/28/2025 | 4 | 2/21/2025 | 2/28/2025 | 4 | 0 | 4 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | France Visa T&C Sidekick | Service Credentials Mapping | 484523 | Deploy | Create SP | Pavan | Robert / Alex / Shiva | FVSK Team |  | 2025 Q1 Sprint4 | 2/21/2025 | 2/28/2025 | 4 | 2/21/2025 | 2/28/2025 | 4 | 0 | 4 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | France Visa T&C Sidekick | Resource Group Creation | 484524 | Deploy | Create RG | Pavan | Robert / Alex / Shiva | FVSK Team |  | 2025 Q1 Sprint4 | 2/21/2025 | 2/28/2025 | 4 | 2/21/2025 | 2/28/2025 | 4 | 0 | 4 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | France Visa T&C Sidekick | TFC Workspace - RG mapping | 484525 | Deploy | Map Workspace to RG | Pavan | Robert / Alex / Shiva | FVSK Team |  | 2025 Q1 Sprint4 | 2/21/2025 | 2/28/2025 | 4 | 2/21/2025 | 2/28/2025 | 4 | 0 | 4 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | France Visa T&C Sidekick | Created Datadog Dashboard | 484526 | Deploy | Datadog Dashboard | Pavan | Robert | FVSK Team |  | 2025 Q1 Sprint4 | 2/21/2025 | 2/28/2025 | 2 | 2/21/2025 | 2/28/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | France Visa T&C Sidekick | Add subscription to Logic Monitor | 484527 | Deploy | Logic Monitor Integration | Pavan | Robert | FVSK Team |  | 2025 Q1 Sprint4 | 2/21/2025 | 2/28/2025 | 2 | 2/21/2025 | 2/28/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | France Visa T&C Sidekick | Add subscription to Datadog | 484528 | Deploy | Datadog Integration | Pavan | Robert | FVSK Team |  | 2025 Q1 Sprint4 | 2/21/2025 | 2/28/2025 | 2 | 2/21/2025 | 2/28/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Onboarding | Azure | France Visa T&C Sidekick | Update Confluence | 484529 | Deploy | Update Confluence | Pavan |  | FVSK Team |  | 2025 Q1 Sprint4 | 2/21/2025 | 2/28/2025 | 2 | 2/21/2025 | 2/28/2025 | 2 | 0 | 2 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Support | AWS | Assurant Labs | ACM Integration with Key Factor | 477342 | Design | ACM Integration with Key Factor | Pavan | Robert / Security Team | Security Team |  | 2025 Q1 Sprint4 | 1/23/2025 | 2/14/2025 | 4 | 1/23/2025 | 2/28/2025 | 4 | 0 | 4 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Support | Azure | SSP Team | [SCTASK1388540] New Resource Groups for SSP | 484309 | Deploy | Create RG | Pavan |  |  |  | 2025 Q1 Sprint4 | 2/17/2025 | 2/19/2025 | 8 | 2/17/2025 | 2/19/2025 | 8 | 0 | 8 | 0 | Complete
2025-02-25 | Assurant | CEP Adoption / App Support | Azure | DSO Team | AKS - Add ability to set the upgrade schedule | 482609 | Deploy | Add feature | Pavan | Robert / Alex |  |  | 2025 Q1 Sprint4 | 2025-04-02 | 2025-12-02 | 4 | 2025-04-02 | 2025-12-02 | 2 | 0 | 2 | -2 | Complete
2025-02-25 | Assurant | CEP Adoption / App Support | Azure | DSO Team | Update to Kubernetes_version variable | 484827 | Deploy | Add feature | Pavan | Robert / Alex |  |  | 2025 Q1 Sprint4 | 2025-04-02 | 2025-12-02 | 8 | 2/25/2025 | 2/28/2025 | 4 | 0 | 4 | -4 | Complete
2025-02-25 | Assurant | CEP Adoption / App Support | Azure | myWorkspace Team | [SCTASK1390704] terraform workspaces for myworkspace | 484530 | Deploy | Workspace creation | Pavan | Shad |  | 80 | 2025 Q1 Sprint5 | 2/21/2025 | 2/25/2025 | 4 | 2/21/2025 | 2/25/2025 | 4 | 0 | 4 | 0 | Complete
2025-03-25 | Assurant | CEP Adoption / App Support | Azure | App Team | [SCTASK1395846] Role assignment for GLAPIM | 484960 | Deploy | Assign Roles | Pavan | Robert |  |  | 2025 Q1 Sprint5 | 2/28/2025 | 2025-02-03 | 8 | 2/28/2025 | 2025-02-03 | 8 | 0 | 8 | 0 | Complete
2025-03-25 | Assurant | CEP Adoption / App Support | Azure | DSO Team | AKS - Add ability to set the upgrade schedule | 482609 | Deploy | Add feature | Pavan | Robert / Alex | 484827 |  | 2025 Q1 Sprint5 | 2/28/2025 | 2025-02-03 | 4 | 2025-04-02 |  | 4 | 2 | 6 | 2 | In Progress
2025-03-25 | Assurant | CEP Adoption / App Support | Azure | DSO Team | Update to Kubernetes_version variable | 484827 | Deploy | Add feature | Pavan | Robert / Alex |  |  | 2025 Q1 Sprint5 | 2025-04-02 | 2025-12-02 | 4 | 2/25/2025 |  | 2 | 2 | 4 | 0 | In Progress
2025-03-25 | Assurant | CEP Adoption / App Support | Azure | App Team | [ SCTASK1397680] create new workspaces for each environment | 485109 | Deploy | Workspace creation | Pavan | Shad |  |  | 2025 Q1 Sprint5 | 2/28/2025 | 2025-02-03 | 8 | 2/28/2025 | 2025-02-03 | 8 | 0 | 8 | 0 | Complete
2025-03-25 | Assurant | CEP Adoption / App Onboarding | Azure | SNOW Azure Translator | Architecture Review |  | Review | SignOff by CEP leads | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, |  |  | 2025 Q1 Sprint5 |  |  | 2 |  |  | 2 | 0 | 2 | 0 | New
2025-03-25 | Assurant | CEP Adoption / App Onboarding | Azure | SNOW Azure Translator | Create App Subscription |  | Deploy | Subscription Creation | Robert | Robert |  |  | 2025 Q1 Sprint5 |  |  | 2 |  |  | 2 | 0 | 2 | 0 | New
2025-03-25 | Assurant | CEP Adoption / App Onboarding | Azure | SNOW Azure Translator | TFE and Greenfield team Onboarding |  | Deploy | TFE Onboarding | Robert, Alex, Shad, Pavan | Robert, Alex, Shad, |  |  | 2025 Q1 Sprint5 |  |  | 2 |  |  | 2 | 0 | 2 | 0 | New
2025-03-25 | Assurant | CEP Adoption / App Onboarding | Azure | SNOW Azure Translator | TFC Workspace Creation |  | Deploy | Workspace creation | Pavan/Shad | Shad |  |  | 2025 Q1 Sprint5 |  |  | 2 |  |  | 2 | 0 | 2 | 0 | New
2025-03-25 | Assurant | CEP Adoption / App Onboarding | Azure | SNOW Azure Translator | Okta groups Creation |  | Deploy | Okta group Creation | Pavan | Okta Team |  |  | 2025 Q1 Sprint5 |  |  | 4 |  |  | 4 | 0 | 4 | 0 | New
2025-03-25 | Assurant | CEP Adoption / App Onboarding | Azure | SNOW Azure Translator | Service Credentials Mapping |  | Deploy | Create SP | Pavan | Robert / Alex / Shiva |  |  | 2025 Q1 Sprint5 |  |  | 4 |  |  | 4 | 0 | 4 | 0 | New
2025-03-25 | Assurant | CEP Adoption / App Onboarding | Azure | SNOW Azure Translator | Resource Group Creation |  | Deploy | Create RG | Pavan | Robert / Alex / Shiva |  |  | 2025 Q1 Sprint5 |  |  | 4 |  |  | 4 | 0 | 4 | 0 | New
2025-03-25 | Assurant | CEP Adoption / App Onboarding | Azure | SNOW Azure Translator | TFC Workspace - RG mapping |  | Deploy | Map Workspace to RG | Pavan | Robert / Alex / Shiva |  |  | 2025 Q1 Sprint5 |  |  | 4 |  |  | 4 | 0 | 4 | 0 | New
2025-03-25 | Assurant | CEP Adoption / App Onboarding | Azure | SNOW Azure Translator | Created Datadog Dashboard |  | Deploy | Datadog Dashboard | Pavan | Robert |  |  | 2025 Q1 Sprint5 |  |  | 2 |  |  | 2 | 0 | 2 | 0 | New
2025-03-25 | Assurant | CEP Adoption / App Onboarding | Azure | SNOW Azure Translator | Add subscription to Logic Monitor |  | Deploy | Logic Monitor Integration | Pavan | Robert |  |  | 2025 Q1 Sprint5 |  |  | 2 |  |  | 2 | 0 | 2 | 0 | New
2025-03-25 | Assurant | CEP Adoption / App Onboarding | Azure | SNOW Azure Translator | Add subscription to Datadog |  | Deploy | Datadog Integration | Pavan | Robert |  |  | 2025 Q1 Sprint5 |  |  | 2 |  |  | 2 | 0 | 2 | 0 | New
2025-03-25 | Assurant | CEP Adoption / App Onboarding | Azure | SNOW Azure Translator | Update Confluence |  | Deploy | Update Confluence | Pavan |  |  |  | 2025 Q1 Sprint5 |  |  | 2 |  |  | 2 | 0 | 2 | 0 | New