## Sheet1
Month | Client Name | Project / Workstream Name | CSP | Application / App Team | Deliverable | Work Item | Product Backlog Item | Type (Plan, Design, Dev, QA, Deploy, Document) | Acceptance Criteria | Team Member | Dependencies | Waiting On | Capacity | Sprint | Estimated Start Data | Estimated End Date | Estimated Effort (Hours) | Actual Start Date | Actual End Date | Actual Effort Hours | ETC (Estimate to Complete) | EAC (Estimate at Completion) | Variance | Status (Completed / Pending) | Remarks
2025-01-25 | Assurant | CEP - Backstage |  |  | Datadog Plugin Analysis | 480096 | 481728 | Plan/Demo | Demo and High Level Approach | Hariharan | None | None | 64 | Sprint 1 | 2025-01-02 | 2025-01-03 | 16 | 2025-01-02 | 2025-01-03 | 16 | 0 | 16 | 0 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | EOL Plugin Analysis | 480096 | 481729 | Plan/Demo | Demo and High Level Approach | Hariharan | None | None |  | Sprint 1 | 2025-01-06 | 2025-01-07 | 16 | 2025-01-06 | 2025-01-07 | 16 | 0 | 16 | 0 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | Github Insights &Pull request Plugin Analysis | 480096 | 481732 | Plan | Demo and High Level Approach | Hariharan | None | None |  | Sprint 1 | 2025-01-08 | 2025-01-08 | 8 | 2025-01-08 | 2025-01-08 | 8 | 0 | 8 | 0 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | Plugin approach Discussions | 480096 | 481732 | Plan/Demo | Demo and High Level Approach | Raj | None | None | 40 | Sprint 1 | 2025-01-07 | 2025-01-07 | 8 | 2025-01-07 | 2025-01-07 | 8 | 0 | 8 | 0 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | Security Insights Plugin Analysis | 480096 | 481730 | Plan | Demo and High Level Approach | Hariharan | None | None |  | Sprint 1 | 2025-01-09 | 2025-01-10 | 16 | 2025-01-09 | 2025-01-10 | 20 | 0 | 20 | 4 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | Software Template LLD Approach | 477134 | 481740 | Design Document | Signoff on LLD | Raj | None | None |  | Sprint 2 | 2025-01-13 | 2025-01-16 | 16 | 2025-01-13 | 2025-01-16 | 18 | 0 | 18 | 2 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | EOL Design Plan | 481738 | 482078 | Design Document | Signoff on LLD | Raj | None | None | 40 | Sprint 2 | 2025-01-17 | 2025-01-17 | 8 | 2025-01-17 | 2025-01-17 | 8 | 0 | 8 | 0 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | Azure Pull Request, Pipeline Analysis | 480096 | 482080 | Plan/Demo | Demo and High Level Approach | Hariharan | None | None | 64 | Sprint 2 | 2025-01-17 | 2025-01-18 | 16 | 2025-01-17 | 2025-01-18 | 17 | 0 | 17 | 1 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | Created ADR for Software Templates, EOL Plugin | 481738 |  | Plan | ADR | Raj | None | None |  | Sprint 2 | 2025-01-21 | 2025-01-21 | 8 | 2025-01-21 | 2025-01-21 | 8 | 0 | 8 | 0 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | Upgrade Backstage version and integrate SW Template | 477134 | 482506 | Dev | E2E Tested SW for Deployment | Hariharan | None | None |  | Sprint 2 | 2025-01-22 | 2025-01-23 | 16 | 2025-01-23 | 2025-01-27 | 24 | 0 | 24 | 8 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | Configure RBAC for Software Template Management | 477134 | 482505 | Dev | E2E Tested SW for Deployment | Hariharan | None | None |  | Sprint 2 | 2025-01-24 | 2025-01-25 | 16 | 2025-01-22 | 2025-01-22 | 8 | 0 | 8 | -8 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | [Domain Heirachy Bot] Create Folder Structure for Organizing Software Templates and Boilerplates | 477134 | 482503 | Dev | E2E test for Deployment | Hariharan | None | None |  | Sprint 2 | 2025-01-26 | 2025-01-26 | 8 | 2025-01-28 | 2025-01-28 | 8 | 0 | 8 | 0 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | ADR, RBAC Discussion & Updated | 477134 | 482505 | Design Document | Signoff on LLD | Raj | None | None |  | Sprint 3 | 2025-01-28 | 2025-01-28 | 8 | 2025-01-28 | 2025-01-28 | 8 | 0 | 8 | 0 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | Resolve Identified Vulnerabilities in Backstage 1.35.0 | 477134 | 483109 | QA | E2E Test | Hariharan | None | None | 80 | Sprint 3 | 2025-01-30 | 2025-01-31 | 16 | 2025-01-30 | 2025-01-31 | 16 | 0 | 16 | 0 | Complete
2025-01-25 | Assurant | CEP - Backstage |  |  | xplore Azure ADO Package to resolve Security Vulnerability for SW Template | 477134 | 483904 | Dev | Resolve Security Vulnerability | Sutharshan | None | None | 40 | Sprint 3 | 2025-02-04 | 2025-02-05 | 8 | 2025-02-04 | 2025-02-05 | 10 | 0 | 10 | 2 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | Enhance Module Dependency Bot to read the List of Programming Languages | 481738 | 482081 | Dev | Module dependency Bot code for Delivery | Hariharan | None | None |  | Sprint 3 | 2025-02-03 | 2025-02-05 | 24 | 2025-02-03 | 2025-02-06 | 32 | 0 | 32 | 8 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | LLD Design Review & Discussions | 481738 | 482081 | Plan |  | Raj | None | None | 40 | Sprint 3 | 2025-02-04 | 2025-02-07 | 8 | 2025-02-04 | 2025-02-07 | 10 | 0 | 10 | 2 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | Display Deprecated Versions via Custom Annotations in Module Dependency Bot & Backstage Portal | 481738 | 482081 | Dev | Module dependency Bot code for Delivery | Hariharan | None | None |  | Sprint 3 | 2025-02-06 | 2025-02-07 | 16 | 2025-02-07 | 2025-02-10 | 16 | 0 | 16 | 0 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | GitHub Release Manager Plugin analysis | 480096 | 483847 | Plan | Demo and High Level Approach | Sutharshan | None | None |  | Sprint 3 | 2025-02-03 | 2025-02-04 | 16 | 2025-02-03 | 2025-02-10 | 16 | 0 | 16 | 0 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | Vulnerabilty Analysis for Software Template Feature | 477134 | 483109 | Dev | Resolve Security Vulnerability | Raj | None | None |  | Sprint 4 | 2025-02-11 | 2025-02-11 | 8 | 2025-02-10 | 2025-02-11 | 8 | 0 | 8 | 0 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | resolve Identified Vulnerabilities in Backstage 1.35.0 | 481738 | 482082 | Dev | Backstage | Hariharan | None | None | 72 | Sprint 4 | 2025-02-11 | 2025-02-11 | 8 | 2025-02-11 | 0-Jan-00 | 20 | 0 | 20 | 12 | Complete | Handled SW Template Modification also for Release
2025-02-25 | Assurant | CEP - Backstage |  |  | Sanity Test,Delivery, Confluence Page Update/Support | 481738 | 482084 | Deployment | E2E Tested SW for Deployment | Raj | None | None | 40 | Sprint 4 | 2025-02-07 | 2025-02-10 | 16 | 2025-02-11 | 2025-02-14 | 16 | 0 | 16 | 0 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | Backstage Documentation Update in Confluence | 480096 | 488536 | Plan | Backstage confluence Page with all Plugin Details | Raj | None | None | 30 | Sprint 8 | 2025-04-09 | 2025-04-10 | 24 | 2025-04-14 | 2025-04-15 | 16 | 0 | 16 | -8 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | Kubernetes Plugin analysis | 480096 |  | Plan | Demo and High Level Approach | Sutharshan | None | None | 36 | Sprint 4 | 2025-02-10 | 2025-02-12 | 24 | 2025-02-11 | 2025-02-17 | 24 | 0 | 24 | 0 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | Pull Request, Security Plugin LLD | 477165 | 482079 | Design Document | Signoff on LLD | Raj/ Hariharan | None | None |  | Sprint 4 | 2025-02-17 | 2025-02-18 | 16 | 2025-02-17 | 2025-02-18 | 16 | 0 | 16 | 0 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | CI/CD Statistics | 480096 | 484412 | Plan | Demo and High Level Approach | Hariharan | None | None |  | Sprint 4 | 2025-02-19 | 2025-02-20 | 16 | 2025-02-20 | 2025-02-21 | 16 | 0 | 16 | 0 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | Kubernetes Plugin analysis | 480096 | 484242 | Plan | Demo and High Level Approach | Sutharshan | None | None |  | Sprint 4 | 2025-02-10 | 2025-02-12 | 24 | 2025-02-11 | 2025-02-17 | 24 | 0 | 24 | 0 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | CI/CD Statistics | 480096 | 484412 | Plan | Demo and High Level Approach | Sutharshan | None | None |  | Sprint 4 | 2025-02-19 | 2025-02-20 | 16 | 2025-02-19 | 2025-02-19 | 8 | 0 | 8 | -8 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | Github Actions Plugin Analysis | 480096 | 484745 | Plan | Demo and High Level Approach | Hariharan | None | None |  | Sprint 4 | 2025-02-17 | 2025-02-19 | 24 | 2025-02-18 | 2025-02-19 | 16 | 0 | 16 | -8 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | Github Actions Plugin Analysis | 480096 | 484745 | Plan | Demo and High Level Approach | Sutharshan | None | None |  | Sprint 4 | 2025-02-17 | 2025-02-19 | 24 | 2025-02-18 | 2025-02-19 | 16 | 0 | 16 | -8 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | Notification Feature Analysis | 480096 | 484963 | Dev | Demo and High Level Approach | Hariharan | None | None | 80 | Sprint 5 | 2025-02-19 | 2025-02-21 | 24 | 2025-02-24 | 2025-02-26 | 24 | 0 | 24 | 0 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | LLD for module-dependency-version-listing | 480096 | 484964 | Plan | LLD Signoff with Shal, Erik, Kali | Hariharan | None | None | 80 | Sprint 6 | 2025-02-21 | 2025-02-22 | 16 | 2025-02-27 | 2025-03-13 | 16 | 0 | 16 | 0 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | LLD for module-dependency-version-listing | 480096 | 484964 | Plan | LLD Signoff with Shal, Erik, Kali | Raj | None | None | 40 | Sprint 6 | 2025-02-21 | 2025-02-22 | 4 | 2025-03-13 | 2025-03-14 | 5 | 0 | 0 | 1 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | Module Dependency Version listing implementation | 480096 | 485424 | Dev | Demo and High Level Approach | Hariharan | LLD Signoff | None |  | Sprint 6 | 2025-03-19 | 2025-03-24 | 40 | 2025-03-14 | 2025-03-18 | 24 | 0 | 24 | -16 | Complete
2025-03-25 | Assurant | CEP - Backstage |  |  | Module-Dependency-Version-Listing UI Implementation. | 480096 | 486643 | Dev | Demo and High Level Approach | Hariharan | None | None |  | Sprint 6 | 2025-03-19 | 2025-03-21 | 24 | 2025-03-19 | 2025-03-21 | 24 | 0 | 24 | 0 | Complete
2025-02-25 | Assurant | CEP - Backstage |  |  | Support/Review for Module Dependency Listing | 480096 | 485424 | Dev | Review the Implementation | Raj | None | None |  | Sprint 6 | 2025-03-20 | 2025-03-20 | 8 | 2025-03-24 | 2025-03-25 | 8 | 0 | 8 | 0 | Complete
2025-03-25 | Assurant | CEP - Backstage |  |  | Notifications module for email | 480096 | 485827 | Dev | Demo and High Level Approach | Hariharan | None | None |  | Sprint 5 | 2025-03-10 | 2025-03-12 | 24 | 2025-03-05 | 2025-03-07 | 24 | 0 | 24 | 0 | Complete
2025-03-25 | Assurant | CEP - Backstage |  |  | Notifications Discussions & Support | 480096 | 485827 | Dev | Demo and High Level Approach | Raj | None | None |  | Sprint 5 | 2025-03-10 | 2025-03-12 | 8 | 2025-03-05 | 2025-03-06 | 8 | 0 | 8 | 0 | Complete
2025-03-25 | Assurant | CEP - Backstage |  |  | Notifications module for teams | 480096 | 485828 | Dev | Demo and High Level Approach | Hariharan | None | None |  | Sprint 5 | 2025-03-13 | 2025-03-17 | 24 | 2025-03-10 | 2025-03-12 | 24 | 0 | 24 | 0 | Complete
2025-03-25 | Assurant | CEP - Backstage |  |  | Team Meeting, Notifications Discussions, ADR Doc Support | 480096 | 485828 | Dev | Demo and High Level Approach | Raj | None | None | 40 | Sprint 5 | 2025-03-13 | 2025-03-17 | 8 | 2025-03-10 | 2025-03-12 | 8 | 0 | 8 | 0 | Complete
2025-03-25 | Assurant | CEP - Backstage |  |  | Code Review and Sanity for 1.6 Release |  |  | Deployment | E2E Tested SW for Deployment | Raj | None | None | 25 | Sprint 9 | 2025-04-24 | 2025-04-25 | 8 | 2025-04-24 | 2025-04-25 | 8 | 0 | 8 | 0 | Complete
2025-03-25 | Assurant | CEP - Backstage |  |  | Update all Documentation for Backstage Handover |  |  | Plan | Sign-off with Shad, Erik, Kali | Hariharan | None | None | 24 | Sprint 9 | 2025-03-26 | 2025-03-28 | 24 | 2025-04-30 | 2025-05-07 | 30 | 0 | 30 | 6 | Complete
2025-03-25 | Assurant | CEP - Backstage |  |  | Backstage Handover Doc Update, Review |  |  | Plan | Sign-off with Shad, Erik, Kali | Raj | None | None | 20 | Sprint 10 | 2025-03-26 | 2025-03-28 | 16 | 2025-05-02 | 2025-05-13 | 24 | 0 | 24 | 8 | Complete
2025-04-25 | Assurant | CEP - Backstage |  |  | Module-Dependency-Version-Listing POC | 478322 | 487355 | Dev | Demo with Shad | Hariharan | None | None |  | Sprint 8 | 2025-04-04 | 2025-04-10 | 24 | 2025-04-04 | 2025-04-10 | 24 | 0 | 24 | 0 | Complete
2025-04-25 | Assurant | CEP - Backstage |  |  | Dependency Listing Chart | 478322 | 487355 | Dev | Demo with Shad | Raj | None | None | 20 | Sprint 8 | 2025-04-09 | 2025-04-10 | 4 | 2025-04-10 | 2025-04-10 | 4 | 0 | 4 | 0 | Complete
2025-04-25 | Assurant | CEP - Backstage |  |  | Module-Dependency - Provision to Exclude Comps from Chart | 478322 | 488122 | Dev | Demo and High Level Approach | Hariharan | None | None | 48 | Sprint 8 | 2025-04-16 | 2025-04-21 | 24 | 2025-04-16 | 2025-04-22 | 32 | 0 | 32 | 8 | Complete
2025-04-25 | Assurant | CEP - Backstage |  |  | Provision to Exclude Comps from Chart Plan/Review | 478322 | 488122 | Dev | Demo and High Level Approach | Raj | None | None |  | Sprint 8 | 2025-04-17 | 2025-04-22 | 6 | 2025-04-16 | 2025-04-16 | 8 | 0 | 8 | 2 | Complete
2025-04-25 | Assurant | CEP - Backstage |  |  | Backstage Release 1.6 Sanity Check and Vulnerability Assessment | 478322 | 488536 | Deploy | Demo and High Level Approach | Hariharan | None | None | 24 | Sprint 9 | 2025-04-23 | 2025-04-25 | 24 | 2025-04-23 | 2025-04-25 | 24 | 0 | 24 | 0 | Complete
2025-03-25 | Assurant | CEP - Backstage |  |  | Token Lifecycle Management | 480096 |  | Plan | Demo and High Level Approach | Hariharan | None | None |  | Deprioritized | 2025-03-05 | 2025-02-07 | 24 |  |  |  | 24 | 24 | 0 | Not Started | Depriotized as there would be data dependency from other Admin Teams
2025-03-25 | Assurant | CEP - Backstage |  |  | GitHub Copilot Adoption Metrics Plugin analysis | 480096 |  | Plan | Demo and High Level Approach | Hariharan | None | None |  | Deprioritized | 2025-03-10 | 2025-03-11 | 16 |  |  |  | 16 | 16 | 0 | Not Started | Depriotized as there would be data dependency from other Admin Teams
2025-02-25 | Assurant | CEP - Backstage |  |  | Module Release Management | 480096 |  | Plan | Demo and High Level Approach | Hariharan | None | None | 40 | Sprint X | 2025-03-19 | 2025-03-20 | 16 |  |  |  | 16 | 16 | 0 | Not Started
2025-03-25 | Assurant | CEP - Backstage |  |  | Wiz | 480096 |  | Plan | Demo and High Level Approach | Raj | None | None |  | Sprint X | 2025-03-21 | 2025-03-24 | 16 |  |  |  | 16 | 16 | 0 | Not Started
2025-03-25 | Assurant | CEP - Backstage |  |  | ADR support for Github | 480096 |  | Dev | Demo and High Level Approach | Hariharan | None | None |  | Sprint X | [6 empty] | 0 | 0 | 0 | Not Started |  | Dependency on Github Migrations
2025-03-25 | Assurant | CEP - Backstage |  |  | Module Dependency Bot: Add GitHub slug annotation | 480096 |  | Dev | Demo and High Level Approach | Hariharan | None | None |  | Sprint X | [6 empty] | 0 | 0 | 0 | Not Started |  | Dependency on Github Migrations
2025-04-25 | Assurant | CEP - Backstage |  |  | Integrate and Deliver Backstage Plugins once the code is Migrated to Github | [8 empty] | Sprint X |  |  | 40 | [6 empty] | Not Started
2025-04-25 | Assurant | CEP - Backstage |  |  | Build Catalog for N/W Services | [8 empty] | Sprint X |  |  | 24 | [6 empty] | Not Started
2025-04-25 | Assurant | CEP - Backstage |  |  | Support or Enhance Backstage based on Adoption Data from Engg TEam | [8 empty] | Sprint X |  |  | 40 | [6 empty] | Not Started