## Sheet1
Month | Client Name | Project / Workstream Name | CSP | Application / App Team | Deliverable | Work Item | Product Backlog Item | Type (Plan, Design, Dev, QA, Deploy, Document) | Acceptance Criteria | Team Member | Dependencies | Waiting On | Capacity | Sprint | Estimated Start Date | Estimated End Date | Estimated Effort (Hours) | Actual Start Date | Actual End Date | Actual Effort Hours | ETC (Estimate to Complete) | EAC (Estimate at Completion) | Variance | Status (Completed / Not Started/In Progress/Submitted) | Remarks
2025-01-25 | Assurant | CEP - Portal |  |  | BE : Adoption Status : Executive Summary | 482090 | 481736 | Dev | An Executive user of CEP Portal should be able to receive an overview of Application adoptions. BE Should be able to provide the necessary information as a single json to FE for display | Sutharsan | None | None | 56 | Sprint 1 | 2025-01-02 | 2025-01-03 | 16 | 2025-01-02 | 2025-01-03 | 16 | 0 | 16 | 0 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | FE : Integrated view of the executive Summary | 482090 | 481741 | Dev | Integrate Executive Summary with Carousel Cards | Petchiammal | None | None |  | Sprint 1 | 2025-01-06 | 2025-01-07 | 16 | 2025-01-06 | 2025-01-07 | 16 | 0 | 16 | 0 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | FE:Code Restructuring Hosted WASM | 482089 | 481743 | Document | Provide detailed document covering What is Hosted WASM, its advantages, our implementation approach. Analyse feasibility | Petchiammal | Review Comments | Kaliraj S |  | Sprint 1 | 2025-01-09 | 2025-01-10 | 16 | 2025-01-09 | 2025-01-10 | 16 | 0 | 16 | 0 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | FE : Codebase Analysis and Document Improvements | 482088 | 481739 | Dev | Analyse and document required code enhancement | Petchiammal | None | None | 72 | Sprint 1 | 2025-01-02 | 2025-01-03 | 16 | 2025-01-02 | 2025-01-03 | 16 | 0 | 16 | 0 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | FE:Codebase refactoring for Enhanced maintainence | 482088 | 481742 | Dev | Refactor code for scalability and Architecture efficiency | Petchiammal | Code Review Comments and Boilerplate | Kaliraj S | 48 | Sprint 2 | 2025-01-08 | 2025-01-16 | 24 | 2025-01-08 | 2025-01-16 | 24 | 0 | 24 | 0 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | BE : Codebase Analysis and Document Improvements | 482088 | 481737 | Dev | Refactor code for scalability and Architecture efficiency | Sutharsan | Code Review Comments | Kaliraj S |  | Sprint 1 | 2025-01-07 | 2025-01-09 | 24 | 2025-01-07 | 2025-01-09 | 24 | 0 | 24 | 0 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | Design and develop system health status data fetch from Portal Backend | 482091 | 481734 | Design | Portal backend should be able to declare its health status to any requstor. | Sutharsan |  | None |  | Sprint 1 | 2025-01-10 | 2025-01-13 | 16 | 2025-01-10 | 2025-01-13 | 16 | 0 | 16 | 0 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | Design health status data fetch from Portal's Python bots | 482091 | 481735 | Design | Portal's bots should be able to declare its health status to any requstor. | Sutharsan | Health APIs for Backstage and Nautobot | None | 40 | Sprint 3 | 2025-01-27 | 2025-01-29 | 16 | 2025-01-27 |  | 8 | 0 | 8 | -8 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | BE : Codebase and Data store Refactoring for information from Grafana Dashboard | 482088 | 482606 | Dev | Refactor code for scalability and Architecture efficiency | Sutharsan | Code Review Comments | Kaliraj S | 64 | Sprint 2 | 2025-01-17 | 2025-01-21 | 24 | 2025-01-17 | 2025-01-21 | 24 | 0 | 24 | 0 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | BE : Codebase and Data store Refactoring for Applications Status | 482088 | 482607 | Dev | Refactor code for scalability and Architecture efficiency | Sutharsan | Code Review Comments | Kaliraj S |  | Sprint 2 | 2025-01-22 | 2025-01-24 | 24 | 2025-01-22 | 2025-01-24 | 24 | 0 | 24 | 0 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | FE:Analysis and Optimization of State Management Approach |  | 483110 | Document | Analyzed the current state management approach, identifying inefficiencies, potential bottlenecks, and areas for improvement in data flow and component interactions while reviewing best practices and evaluating alternative solutions to optimize performance and maintainability | Petchiammal | None | None |  | Sprint 2 | 2025-01-17 | 2025-01-20 | 16 | 2025-01-17 | 2025-01-20 | 16 | 0 | 16 | 0 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | FE:Refactoring and Enhancing State Management for Improved Performance |  | 483111 | Dev | Refactored state management logic to improve efficiency and maintainability, optimizing data flow to reduce unnecessary re-renders while implementing best practices to enhance scalability and modularity. | Petchiammal | None | None |  | Sprint 2 | 2025-01-23 | 2025-01-24 | 16 | 2025-01-23 | 2025-01-24 | 16 | 0 | 16 | 0 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | FE:Internal Application Status UX Design |  | 483112 | Dev | Designed the user experience for the Internal Application Status module, focusing on usability and accessibility. | Petchiammal | None | None | 72 | Sprint 3 | 2025-01-27 | 2025-01-28 | 16 | 2025-01-27 | 2025-01-28 | 16 | 0 | 16 | 0 | Completed
2025-02-25 | Assurant | CEP - Portal |  |  | FE:Internal Application Status UI Implementation |  | 483113 | Dev | Developed and implemented the UI based on the UX design while ensuring responsiveness, accessibility, and a seamless user experience. | Petchiammal | None | None |  | Sprint 3 | 2025-01-29 | 2025-02-04 | 24 | 2025-01-29 | 2025-02-05 | 24 | 0 | 24 | 0 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | Notifications Pinned Messages Improvisation |  | 483114 | Dev | Pinned Messages should be included in the notifications YAML instead of using a separate YAML file | Sutharsan | None | None |  | Sprint 2 | 2025-01-27 | 2025-01-27 | 8 | 2025-01-27 | 2025-01-27 | 8 | 0 | 8 | 0 | Completed
2025-01-25 | Assurant | CEP - Portal |  |  | Design and develop health status data fetch from Portal's Python bots | 482091 | 481735 | Dev |  | Sutharsan | None | None |  | Sprint 3 | 2025-01-28 | 2025-01-30 | 24 | 2025-01-28 | 2025-01-30 | 24 | 0 | 24 | 0 | Completed
2025-02-25 | Assurant | CEP - Portal |  |  | BE : Unit tests for portal backend |  |  | Dev | All paths of code should be unit testable using test framework | Sutharsan | None | None | 36 | Sprint 4 | 2025-02-10 | 2025-02-14 | 40 | 2025-02-10 |  | 8 | 0 | 8 | -32 | Completed
2025-02-25 | Assurant | CEP - Portal |  |  | Building Backlogs Items in the Spoke and Workspace Configurations. |  | 483858 | Plan | Build Product Backlog | Sutharsan | None | None |  | Sprint 3 | 2025-02-06 | 2025-02-07 | 16 | 2025-02-06 | 2025-02-07 | 16 | 0 | 16 | 0 | Completed
2025-02-25 | Assurant | CEP - Portal |  |  | Building Backlogs Items in the Spoke and Workspace Configurations. |  | 483858 | Plan | Build Product Backlog | Petchiammal | None | None |  | Sprint 3 | 2025-02-06 | 2025-02-07 | 16 | 2025-02-06 | 2025-02-07 | 16 | 0 | 16 | 0 | Completed
2025-02-25 | Assurant | CEP - Portal |  |  | FE: State Management Handling |  |  | Dev | State Mgmt Handling as per the review comments | Petchiammal | None | None | 56 | Sprint 4 | 2025-02-05 | 2025-02-11 | 40 | 2025-02-11 | 2025-02-14 | 32 | 0 | 32 | -8 | Completed
2025-02-25 | Assurant | CEP - Portal |  |  | Analysis and Plan PBI for the the Spoke and Workspace Configurations |  | 484746 | Document | Analyzed and Plan PBI for the Spoke and Workspace Configurations | Sutharsan | None | None |  | Sprint 4 | 2025-02-20 | 2025-02-24 | 24 | 2025-02-20 | 2025-02-24 | 24 | 0 | 24 | 0 | Completed
2025-02-25 | Assurant | CEP - Portal |  |  | BE : Unit tests for portal backend |  | 484965 | Dev | All paths of code should be unit testable using test framework | Sutharsan | None | None | 80 | Sprint 5 | 2025-02-25 | 2025-02-28 | 40 | 2025-02-25 | 2025-02-28 | 40 | 0 | 40 | 0 | Completed
2025-03-25 | Assurant | CEP - Portal |  |  | BE : Unit tests for python bots |  | 485426 | Dev | All paths of code should be unit testable using test framework | Sutharsan | None | None |  | Sprint 5 | 2025-03-03 | 2025-03-07 | 40 | 2025-03-03 | 2025-03-07 | 40 | 0 | 40 | 0 | Completed
2025-03-25 | Assurant | CEP - Portal |  |  | UX for Spoke and Workspace Configurations |  | 485427 | Document | Define and document the UX design plan for Spoke and Workspace configurations | Petchiammal | None | None | 80 | Sprint 5 | 2025-03-03 | 2025-03-07 | 40 | 2025-03-03 | 2025-03-10 | 48 | 0 | 48 | 8 | Completed
2025-03-25 | Assurant | CEP - Portal |  | 485425 | LLD Documentation for CEP Portal |  | 485425 | Document | Identify and document any missing Low-Level Designs (LLDs) or required updates to existing LLDs. | Hariharan | None | None | 80 | Sprint 5 | 2025-03-03 | 2025-03-05 | 24 | 2025-03-03 | 2025-03-13 | 16 | 0 | 16 | -8 | Completed
2025-03-25 | Assurant | CEP - Portal |  |  | FE: architecture design outlining request type selection logic. |  | 486110 | Document | Create a detailed architecture design outlining request type selection logic, backend interactions, and validation flow. | Petchiammal | None | None | 56 | Sprint 6 | 2025-03-11 | 2025-03-12 | 16 | 2025-03-11 | 2025-03-12 | 16 | 0 | 16 | 0 | Completed
2025-03-25 | Assurant | CEP - Portal |  |  | Refining UX for Spoke and Workspace Configurations - Azure onboarding |  | 486211 | Design | Refining UX for Spoke and Workspace Configurations - Azure onboarding | Petchiammal | None | None |  | Sprint 6 | 2025-03-13 | 2025-03-18 | 32 | 2025-03-13 | 2025-03-18 | 32 | 0 | 32 | 0 | Completed
2025-03-25 | Assurant | CEP - Portal |  |  | UX Review and Support |  | 486110 | UX Design Document | Ux for Azure , Spoke Service Configuration Support for the Team | Raj | None | None | 48 | Sprint 6 | 2025-03-11 | 2025-03-18 | 24 | 2025-03-11 | 2025-03-18 | 30 | 0 | 30 | 6 | Completed
2025-03-25 | Assurant | CEP - Portal |  |  | FE:Develop the UI for request type selection & Project Overview Form | 486972 | 486109 | Development | Implement UI for selecting request types and Project overview | Petchiammal | None | None |  | Sprint 6 | 2025-03-19 | 2025-03-21 | 24 | 2025-03-24 | 2025-03-24 | 8 | 0 | 8 | -16 | Completed
2025-03-25 | Assurant | CEP - Portal |  |  | Create/Review a High Live Design Document for Spoke & Workspace Configuration | 486972 | 486942 | Design | Sign off with Shad | Raj |  |  |  | Sprint 6 | 2025-03-19 | 2025-03-21 | 24 | 2025-03-19 |  | 24 | 0 | 24 | 0 | Completed
2025-03-25 | Assurant | CEP - Portal |  |  | FE:Develop UI for Customer Requirements Form | 486972 | 486862 | Development | UI Screen Development as per Approved UX | Petchiammal | None | None |  | Sprint 7 | 2025-03-26 | 2025-03-27 | 16 | 2025-03-25 | 2025-03-25 | 10 | 0 | 10 | -6 | Completed
2025-03-25 | Assurant | CEP - Portal |  |  | FE:Develop UI for Environment and Terraform Fields Form | 486972 | 486863 | Development | UI Screen Development as per Approved UX | Petchiammal | None | None | 80 | Sprint 7 | 2025-03-28 | 2025-04-01 | 24 | 2025-03-26 | 2025-03-28 | 30 | 0 | 30 | 6 | Completed
2025-03-25 | Assurant | CEP - Portal |  |  | FE:Develop UI for Terraform & Workspace Configuration Form | 486972 | 486864 | Development | UI Screen Development as per Approved UX | Petchiammal | None | None |  | Sprint 7 | 2025-04-02 | 2025-04-04 | 24 | 2025-03-31 | 2025-03-31 | 8 | 0 | 8 | -16 | Completed
2025-03-25 | Assurant | CEP - Portal | 486972 | 486942 | LLD, ERD Design for Request Selection, Customer Req Feature |  |  | Design | Sign off with Shad | Hariharan | None | None | 60 | Sprint 7 | 2025-03-26 | 2025-04-01 | 40 | 2025-03-24 | 2025-04-01 | 48 | 0 | 48 | 8 | Completed
2025-03-25 | Assurant | CEP - Portal |  |  | LLD, ERD Design for Environment, Network, Terraform Fields | 486972 | 486942 | Design | Sign off with Shad | Raj | None | None |  | Sprint 7 | 2025-03-26 | 2025-04-01 | 40 | 2025-03-24 |  | 40 | 0 | 40 | 0 | Completed
2025-04-25 | Assurant | CEP - Portal |  |  | FE:Develop UI for Network Configurations Page | 486972 | 486865 | Development | UI Screen Development as per Approved UX | Petchiammal | None | None |  | Sprint 7 | 2025-04-01 | 2025-04-01 | 8 | 2025-04-01 | 2025-04-03 | 24 | 0 | 24 | 16 | Completed
2025-04-25 | Assurant | CEP - Portal |  |  | FE:Develop UI for Observability Requirement Page |  |  | Development | UI Screen Development as per Approved UX | Petchiammal | None | None |  | Sprint 7 | 2025-04-02 | 2025-04-03 | 16 | 2025-04-04 | 2025-04-04 | 8 | 0 | 8 | -8 | Completed
2025-04-25 | Assurant | CEP - Portal |  |  | FRD Analysis for AWS and Create a FRD Doc |  |  | Plan | Sign off with Shad | Hariharan | None | None |  | Sprint 7 | 2025-04-01 | 2025-04-02 | 16 | 2025-04-02 | 2025-04-08 | 20 | 0 | 20 | 4 | Completed
2025-04-25 | Assurant | CEP - Portal |  |  | UX For AWS Workspace Configuration |  |  | Plan | Review with Shad/Erik/Kali | Raj | None | None |  | Sprint 7 | 2025-04-07 | 2025-04-08 | 16 | 2025-04-04 | 2025-04-08 | 16 | 0 | 16 | 0 | Completed
2025-04-25 | Assurant | CEP - Portal |  |  | AWS Workspace Plan FRD Analysis |  |  | Plan | User Stories Breakdown | Raj | None | None | 70 | Sprint 7 | 2025-04-02 | 2025-04-04 | 24 | 2025-04-01 | 2025-04-03 | 24 | 0 | 24 | 0 | Completed
2025-04-25 | Assurant | CEP-Portal |  |  | FE: Develop UI for Preview page | 486972 | 487727 | Development | Implement UI for Preview Page | Petchiammal | None | None |  | Sprint 7 | 2025-04-07 | 2025-04-08 | 16 | 2025-04-07 | 2025-04-08 | 16 | 0 | 16 | 0 | Completed
2025-04-25 | Assurant | CEP-Portal |  |  | FE: UI changes for Form Submission | 486972 | 487728 | Development | Work on UI changes as per comments received | Petchiammal | None | None |  | Sprint 8 | 2025-04-09 | 2025-04-09 | 8 | 2025-04-09 | 2025-04-09 | 8 | 0 | 8 | 0 | Completed
2025-04-25 | Assurant | CEP-Portal |  |  | FE:Develop UI for Reviewer Pages | 486972 | 486868 | Development | Implement UI for Reviewer Page, Reviewer Detail Page | Petchiammal | None | None | 64 | Sprint 8 | 2025-04-09 | 2025-04-11 | 16 | 2025-04-15 | 2025-04-16 | 16 | 0 | 16 | 0 | Completed
2025-04-25 | Assurant | CEP - Portal |  |  | FE:Develop UI for My Project Page | 486972 | 486867 | Development | Implement UI for My Project with status filter | Petchiammal | None | None |  | Sprint 8 | 2025-04-04 | 2025-04-07 | 8 | 2025-04-10 | 2025-04-10 | 8 | 0 | 8 | 0 | Completed
2025-04-25 | Assurant | CEP-Portal |  |  | FE: Create Functional Reqquirement Documentation for spoke and workspace configuration | 486972 | 488121 | Document | Create Functional Reqquirement Documentation for spoke and workspace configuration | Petchiammal | None | None |  | Sprint 8 | 2025-04-11 | 2025-04-14 | 16 | 2025-04-11 | 2025-04-14 | 16 | 0 | 16 | 0 | Completed
2025-04-25 | Assurant | CEP-Portal |  |  | FRD Review and Updates | 486972 | 488121 | Document |  | Raj | None | None | 40 | Sprint 8 | 2025-04-14 | 2025-04-15 | 12 | 2025-04-14 | 2025-04-15 | 15 | 0 | 15 | 3 | Completed
2025-04-25 | Assurant | CEP-Portal |  |  | Boilerplate Walkthrough , HLD Arch update for Azure/AWS after Review | 491088 |  | Plan |  | Raj |  | Tech Debt with Kali | 48 | Sprint 10 | 2025-05-08 | 2025-05-13 | 24 | 2025-05-08 | 2025-05-12 | 15 | 0 | 15 | -9 | Completed
2025-04-25 | Assurant | CEP-Portal |  |  | FE: Reviewer Page - Add Edit Meta Data UI Functionality | 486972 | 487352 | Development | Develop an interactive user interface that enables reviewers to view and edit requestor metadata | Petchiammal | None | None |  | Sprint 8 | 2025-04-14 | 2025-04-15 | 8 | 2025-04-17 | 2025-04-21 | 16 | 0 | 16 | 8 | Completed
2025-04-25 | Assurant | CEP-Portal |  |  | FE: Reviewer Page - Add FAQ Updation Page | 486972 | 487353 | Development | Develop an interactive user interface that enables reviewers to view ,update and add new FAQ section | Petchiammal | None | None |  | Sprint 9 | 2025-04-16 | 2025-04-18 | 24 | 2025-04-22 | 2025-04-24 | 24 | 0 | 24 | 0 | Completed
2025-04-25 | Assurant | CEP - Portal |  |  | CEP Portal, Backstage Engineering Portal Backlog/Plan for 2025 - Team Meeting |  |  | Plan |  | Raj | None | None | 10 | Sprint 9 | 2025-04-22 | 2025-04-23 | 10 | 2025-04-28 | 2025-04-29 | 10 | 0 | 10 | 0 | Completed
2025-04-25 | Assurant | CEP-Portal |  |  | FE:Develop UI for AWS Onboarding | 486972 | 487354 | Development | Develop an interactive user interface form for aws onboarding | Petchiammal | None | None | 72 | Sprint 9 | 2025-04-25 | 2025-04-30 | 32 | 2025-04-25 | 2025-04-29 | 32 | 0 | 32 | 0 | Completed
2025-04-25 | Assurant | CEP-Portal |  |  | FE:UI changes for AWS Onboarding | 486972 | 488863 | Development | Work on Ui Changes as per comments received | Petchiammal | None | None |  | Sprint 9 | 2025-04-30 | 2025-04-05 | 24 | 2025-04-30 | 2025-05-06 | 40 | 0 | 40 | 16 | Completed
2025-05-05 | Assurant | CEP-Portal |  |  | UX Updation for Spoke and Workspace Configurations | 486972 | 489735 | Document | Update the discussed changes on ux for spoke and workspace configuration | Petchiammal | None | None |  | Sprint 10 | 2025-05-07 | 2025-05-08 | 16 | 2025-05-07 | 2025-05-08 | 16 | 0 | 16 | 0 | Completed
2025-04-25 | Assurant | CEP-Portal |  |  | Documentation for Azure Onboarding Process | 486972 | 487729 | Plan | Create technical documentation for Azure Onboarding in Spoke and Workspace configuration. | Hariharan | None | None | 40 | Sprint 8 | 2025-04-11 | 2025-04-15 | 16 | 2025-04-11 | 2025-04-15 | 16 | 0 | 16 | 0 | Completed
2025-04-25 | Assurant | CEP - Portal |  |  | Backend platform bringup and log | 486972 | 488857 | Development | Document Backend platform bringup and log | Hariharan | None | None | 24 | Sprint 9 | 2025-04-28 | 2025-04-29 | 24 | 2025-04-28 | 2025-04-30 | 24 | 0 | 24 | 0 | Completed
2025-05-05 | Assurant | CEP-Portal |  |  | Backend Code Migration: Grafana & Metadata to Boilerplate V2 | 482089 | 489732 | Development | Migrate the BE codebase to new boilerplate | Hariharan | None | None | 80 | Sprint 10 | 2025-05-08 | 2025-05-13 | 40 | 2025-05-08 | 2025-05-13 | 40 | 0 | 40 | 0 | Completed
2025-05-05 | Assurant | CEP-Portal |  |  | Backend Code Migration: Grafana & Metadata to Boilerplate V2 - Support/Review | 482089 | 489732 | Development | Migrate the BE codebase to new boilerplate | Raj | None | None |  | Sprint 10 | 2025-05-12 | 2025-05-13 | 8 | 2025-05-12 | 2025-05-13 | 13 | 0 | 13 | 5 | Completed
2025-05-05 | Assurant | CEP-Portal |  |  | Frontend Migration Review/Discussion on Azure and AWS Workspace Configurations | 489734 |  |  |  | Raj |  |  |  | Sprint 10 | 2025-05-12 | 2025-05-16 | 8 | 2025-05-12 | 2025-05-16 | 5 | 0 | 5 | -3 | Completed
2025-04-25 | Assurant | CEP-Portal |  |  | HLD Design update for all the Workspace Configuration |  |  | Design | Sign off with Shad | Raj | None | Kali to Sign-off |  | Sprint 8 | 2025-04-18 | 2025-04-22 | 24 | 2025-04-17 | 2025-04-22 | 24 | 0 | 24 | 0 | Completed
2025-05-05 | Assurant | CEP - Portal |  |  | [Azure]Spoke Service and Workspace UI Migration to New Boilerplate Code | 482089 | 489734 | Development |  | Petchiammal |  | None | 80 | Sprint 10 | 2025-05-06 | 2025-05-20 | 64 | 2025-05-09 | 2025-05-21 | 64 | 0 | 64 | 0 | Completed
2025-05-05 | Assurant | CEP - Portal |  |  | [AWS]Spoke Service and Workspace UI Migration to New Boilerplate Code | 482089 | 490716 | Development |  | Petchiammal |  | None | 80 | Sprint 11 | 2025-05-22 | 2025-05-23 | 16 | 2025-05-22 | 2025-05-27 | 32 | 0 | 32 | 16 | Completed
2025-05-05 | Assurant | CEP - Portal |  |  | Analysis for front-end integration, aligning the existing structure with backend services. | 491082 |  | Development |  | Petchiammal | None | None |  | Sprint 11 | 2025-05-28 | 2025-05-29 | 16 | 2025-05-28 | 2025-05-29 | 16 | 0 | 16 | 0 | Completed
2025-05-05 | Assurant | CEP-Portal |  |  | Migration of Existing Grafana Dashboards to Boilerplate | 482089 | 490279 | Development | Migrate the FE grafana dashboard codebase to new boilerplate | Hariharan | None | None |  | Sprint 10 | 2025-05-14 | 2025-05-20 | 40 | 2025-05-14 | 2025-05-22 | 32 | 0 | 32 | -8 | Completed
2025-05-05 | Assurant | CEP-Portal |  |  | Migration of Existing Grafana Dashboards to Boilerplate | 482089 | 490279 | Plan | Migration Dicussion, review meet | Raj | None | None |  | Sprint 10 | 2025-05-16 | 2025-05-20 | 16 | 2025-05-15 | 2025-05-19 | 10 | 0 | 10 | -6 | Completed
2025-05-05 | Assurant | CEP-Portal |  |  | Feature Flag POC | 490753 |  | Development |  | Raj | None | None |  | Sprint 10 | 2025-05-20 | 2025-05-20 | 8 | 2025-05-20 | 2025-05-20 | 8 | 0 | 8 | 0 | Completed
2025-05-05 | Assurant | CEP-Portal |  |  | FAQ Management in Portal | 491085 |  | Plan |  | Raj | None | None |  | Sprint 11 | 2025-05-26 | 2025-05-26 | 16 | 2025-05-26 | 2025-05-27 | 13 | 0 | 13 | -3 | Completed
2025-05-05 | Assurant | CEP-Portal |  |  | LLD Walthough,Review/discussion on Drafted backend checklist for full implementation: request creation, validation, status updates, role-based access, audit logging, and error handling | 491084 |  | Development |  | Raj | None | None | 48 | Sprint 11 | 2025-05-27 | 2025-05-30 | 16 | 2025-05-28 | 2025-05-30 | 14 | 0 | 14 | -2 | Completed
2025-05-05 | Assurant | CEP-Portal |  |  | Feature Flag POC | 486972 | 490753 | Development | Implement the Feature Flag Management to control features in both FE and BE | Hariharan | None | None |  | Sprint 11 | 2025-05-20 | 2025-05-21 | 16 | 2025-05-20 | 2025-05-21 | 16 | 0 | 16 | 0 | Completed
2025-05-05 | Assurant | CEP-Portal |  |  | Researched use cases and drafted high-level approach for FAQ management in the portal, including user roles, content lifecycle, and access controls. | 491085 |  | Development | Initial Approach Plan for FAQ Managment | Hariharan | None | None | 64 | Sprint 11 | 2025-05-26 | 2025-05-26 | 8 | 2025-05-26 | 2025-05-26 | 8 | 0 | 8 | 0 | Completed
2025-05-05 | Assurant | CEP - Portal |  |  | Set up foundational backend structure — defined DTOs, service scaffolding, and initial database schema for Spoke/Workspace request flow. Drafted backend checklist for full implementation: request creation, validation, status updates, role-based access, audit logging, and error handling | 491084 |  | Development |  | Hariharan | None |  |  | Sprint 11 | 2025-05-27 | 2025-06-03 | 40 | 2025-05-27 | 2025-06-03 | 41 | 0 | 41 | 1 | Completed
2025-06-25 | Assurant | CEP-Portal |  |  | [BE]Implement Checklist Items CRUD Operations |  |  | Development | CRUD Operations for Template Mgmt | Hariharan | None | None | 80 | Sprint 12 | 2025-06-04 | 2025-06-06 | 24 | 2025-06-04 | 2025-06-06 | 24 | 0 | 24 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | [FE]Create Cloud Provider Overview |  |  | Development |  | Hariharan | None | None |  | Sprint 12 | 2025-06-09 | 2025-06-11 | 24 | 2025-06-09 | 2025-06-10 | 16 | 0 | 16 | -8 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Create Schema, List of Services for Workspace configuration | 491084 | 491084 | Development |  | Raj | None | None | 50 | Sprint 12 | 2025-06-04 | 2025-06-06 | 16 | 2025-06-02 | 2025-06-05 | 26 | 0 | 26 | 10 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Templates Managment |  | 491568 | Development |  | Raj | None | None |  | Sprint 12 | 2025-06-09 | 2025-06-11 | 24 | 2025-06-09 | 2025-06-11 | 20 | 0 | 20 | -4 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Implement Onboarding Request for Azure |  |  | Development |  | Hariharan | None | None |  | Sprint 12 | 2025-06-12 | 2025-06-13 | 16 | 2025-06-11 | 2025-06-12 | 16 | 0 | 16 | 0 | Completed | Redesigned the Approach
2025-06-25 | Assurant | CEP - Portal |  |  | Dynamic Form Builder to Onboard any Platform |  | 492151 | Development |  | Raj | None | None |  | Sprint 12 | 2025-06-12 | 2025-06-16 | 16 | 2025-06-12 | 2025-06-13 | 12 | 0 | 12 | -4 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Integration:Customer Requirements Form Submission | 491158 | 491083 | Development |  | Petchiammal | None | None |  | Sprint 11 | 2025-05-30 | 2025-06-03 | 24 | 2025-05-30 | 2025-06-03 | 24 | 0 | 24 | 0 | Completed | Redesigned the Approach
2025-06-25 | Assurant | CEP - Portal |  |  | Build Template Overview Page | 491158 | 491564 | Development |  | Petchiammal | None | None |  | Sprint 12 | 2025-06-04 | 2025-06-05 | 24 | 2025-06-04 | 2025-06-06 | 24 | 0 | 24 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Frontend UI Implementation of Checklist Progress Page |  | 491086 | Development |  | Sutharsan | None | None | 20 | Sprint 11 | 2025-05-29 | 2025-05-30 | 10 | 2025-05-29 | 2025-06-03 | 18 | 0 | 18 | 8 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Create Template for Form Creation | 491158 | 491569 | Development |  | Petchiammal | None | None | 80 | Sprint 12 | 2025-06-09 | 2025-06-09 | 16 | 2025-06-09 | 2025-06-11 | 24 | 0 | 24 | 8 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Edit Templates Task for Form Creation | 491158 | 491570 | Development |  | Petchiammal | None | None |  | Sprint 12 | 2025-06-10 | 2025-06-11 | 16 | 2025-06-12 | 2025-06-13 | 16 | 0 | 16 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Create and Integrate Template Management Dashboard | 491158 | 491568 | Development |  | Sutharsan | None | None | 30 | Sprint 12 | 2025-06-04 | 2025-06-06 | 16 | 2025-06-05 | 2025-06-09 | 24 | 0 | 24 | 8 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Team Sync-up, Review on the Progress on Questionare mgmt |  | 491973 | Development |  | Raj | None | None |  | Sprint 12 | 2025-06-11 | 2025-06-12 | 6 | 2025-06-17 | 2025-06-17 | 6 | 0 | 6 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Worked on design Approach for Global Reusable Components (e.g., Subnets, VNETs) |  | 492695 | Plan |  | Raj | None | None | 62 | Sprint 13 | 2025-06-20 | 2025-06-24 | 7 | 2025-06-20 | 2025-06-24 | 7 | 0 | 7 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | [FE]POC on Dynamic Form Building for different Providers | 491972 | 492154 | Development | Demo | Petchiammal | None | None |  | Sprint 12 | 2025-06-16 | 2025-06-18 | 24 | 2025-06-16 | 2025-06-18 | 24 | 0 | 24 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Create Template Engine to process the Questionaries for Providers | 491972 | 492152 | Development |  | Petchiammal | None | None | 16 | Sprint 13 | 2025-06-19 | 2025-06-20 | 16 | 2025-06-19 | 2025-06-20 | 16 | 0 | 16 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Generate a Ticket No. for a request using 6 digit random generator by pre-filler |  |  | Development |  | Hariharan | None | None |  | Sprint 12 | 2025-06-13 | 2025-06-13 | 8 | 2025-06-13 | 2025-06-13 | 8 | 0 | 8 | 0 | Completed
2025-06-25 | Assurant | CEP-Portal |  |  | FRD/HLD/LLD for CEp Portal Features |  | 492739 | Documentation |  | Raj | None | None |  | Sprint 13 | 2025-06-20 | 2025-07-02 | 20 | 2025-06-20 |  | 28 | 0 | 28 | 8 | Completed
2025-06-25 | Assurant | CEP-Portal |  |  | [BE]CRUD operations for Questionaries | 491972 | 491979 | Development |  | Hariharan | None | None |  | Sprint 12 | 2025-06-16 | 2025-06-18 | 24 | 2025-06-16 | 2025-06-18 | 24 | 0 | 24 | 0 | Completed
2025-06-25 | Assurant | CEP-Portal |  |  | Design Approach for Global Reusable Components (e.g., Subnets, VNETs |  | 492695 | Plan |  | Hariharan | None | None |  | Sprint 13 | 2025-06-20 | 2025-06-25 | 24 | 2025-06-20 | 2025-06-24 | 24 | 0 | 24 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Build a Template Auto-Cloning Service that is triggered when an onboarding request is initiated |  |  | Development |  | Hariharan | None | None | 64 | Sprint 13 | 2025-06-24 | 2025-06-25 | 16 | 2025-06-19 | 2025-06-20 | 16 | 0 | 16 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Add Template Activation Controls | 491158 | 491971 | Development |  | Sutharsan | None | None |  | Sprint 12 | 2025-06-09 | 2025-06-13 | 24 | 2025-06-10 | 2025-06-13 | 32 | 0 | 32 | 8 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | [FE]Questionnaire Form Builder for Platform | 491972 | 491973 | Development |  | Sutharsan | None | None |  | Sprint 12 | 2025-06-16 | 2025-06-18 | 24 | 2025-06-16 | 2025-06-18 | 24 | 0 | 24 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Gantt Chatt UI for Checklist item workflow builder | 491972 | 492651 | Development |  | Sutharsan | None | None | 64 | Sprint 13 | 2025-06-19 | 2025-06-19 | 8 | 2025-06-19 | 2025-06-19 | 8 | 0 | 8 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Documentation Application Metadata Fetaure |  | 492652 | Documentation |  | Sutharsan | None | None |  | Sprint 13 | 2025-06-25 | 2025-06-25 | 4 | 2025-06-25 | 2025-06-25 | 4 | 0 | 4 | 0 | Completed
2025-06-25 | Assurant | CEP-Portal |  |  | Dynamic Form Fields Sync-up/Code Review/Testing | 491972 | 492159 | Plan |  | Raj | None | None |  | Sprint 13 | 2025-06-19 | 2025-07-02 | 12 | 2025-06-16 | 2025-07-02 | 26 | 0 | 26 | 14 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | Modify backend design with the modified design goals |  | 492738 | Development |  | Hariharan | None | None |  | Sprint 13 | 2025-06-26 | 2025-06-30 | 24 | 2025-06-26 | 2025-06-30 | 24 | 0 | 24 |  | Completed
2025-07-25 | Assurant | CEP - Portal |  |  | Implementation of PresetDefinition (GlobalComponent) CRUD | 491158 | 493326 | Development |  | Hariharan | None | None | 80 | Sprint 14 | 2025-07-01 | 2025-07-03 | 24 | 2025-07-01 | 2025-07-03 | 24 | 0 | 24 | 0 | Completed
2025-07-25 | Assurant | CEP - Portal |  |  | Enhancement of Questionnaire Management | 491158 | 493325 | Development |  | Hariharan | None | None |  | Sprint 14 | 2025-07-04 | 2025-07-08 | 24 | 2025-07-04 | 2025-07-08 | 32 | 0 | 32 | 8 | Completed
2025-07-25 | Assurant | CEP - Portal |  |  | Enhancement of Questions module within the Questionnaire Management system | 491158 | 493324 | Development |  | Hariharan | None | None |  | Sprint 14 | 2025-07-09 | 2025-07-10 | 16 | 2025-07-09 | 2025-07-16 | 32 | 0 | 24 | 8 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | [FE]Global Components Builder | 491972 | 492155 | Development |  | Sutharsan | None | None | 80 | Sprint 14 | 2025-07-01 | 2025-07-03 | 24 | 2025-07-01 | 2025-07-03 | 24 | 0 | 24 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | [FE]Questionnaire Form Builder with Support for Global Components | 491972 | 492156 | Development |  | Sutharsan | None | None |  | Sprint 14 | 2025-07-04 | 2025-07-09 | 24 | 2025-07-04 | 2025-07-09 | 32 | 0 | 32 | 8 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | [FE]Platform questionnaire/Form field clone Feature | 491972 | 492157 | Development |  | Sutharsan | None | None |  | Sprint 14 | 2025-07-10 | 2025-06-11 | 16 | 2025-07-10 | 2025-07-11 | 16 | 0 | 16 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | [FE]Create Template Engine to process the Questionaries for Providers | 491972 | 492152 | Development |  | Sutharsan | None | None |  | Sprint 14 | 2025-06-19 | 2025-06-20 | 16 | 2025-07-14 | 2025-07-14 | 8 | 0 | 8 | -8 | Completed
2025-07-25 | Assurant | CEP - Portal |  |  | Dynamic Rendering of Forms based on Selected Platform | 491158 | 493327 | Development |  | Sutharsan | None | None |  | Sprint 14 | 2025-07-15 | 2025-07-16 | 16 | 2025-07-15 | 2025-07-16 | 16 | 0 | 16 | 0 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | [FE]Create Platform Page and Integrate with backend API | 491972 | 492153 | Development |  | Raj | None | None | 40 | Sprint 14 | 2025-06-26 | 2025-06-26 | 16 | 2025-07-04 | 2025-07-08 | 24 | 0 | 24 | 8 | Completed
2025-06-25 | Assurant | CEP - Portal |  |  | [FE]Create Dynamic Form Fields based on the Selected Platform | 491972 | 491974 | Development |  | Raj | None | None |  | Sprint 15 | 2025-07-17 | 2025-07-21 | 8 |  |  | 0 | 8 | 8 | 0 | InProgress
2025-06-25 | Assurant | CEP - Portal |  |  | Team Sync up/Code Review/ Meetings/Sprint Meeting/Board Update | 491972 | 493341 | Plan |  | Raj | None | None | 50 | Sprint 15 | 2025-07-03 | 2025-07-16 | 30 | 2025-07-03 | 2025-07-16 | 30 | 10 | 40 | 10 | InProgress
2025-07-25 | Assurant | CEP - Portal |  |  | Create OnboardingRequest entity and respective endpoints needed for Questionnaire Session | 493330 | 493332 | Development |  | Hariharan | None | None |  | Sprint 15 | 2025-07-17 | 2025-07-21 | 20 |  |  | 0 | 20 | 20 | 0 | InProgress
2025-07-25 | Assurant | CEP - Portal |  |  | Enhance Application Entity for OnboardingRequest | 493330 | 493333 | Development |  | Hariharan | None | None | 80 | Sprint 15 | 2025-07-21 | 2025-07-22 | 12 |  |  | 0 | 12 | 12 | 0 | Not Started
2025-07-25 | Assurant | CEP - Portal |  |  | Create Questionnaire Session Management | 493330 | 493334 | Development |  | Hariharan | None | None |  | Sprint 15 | 2025-07-23 | 2025-07-25 | 24 |  |  | 0 | 24 | 24 | 0 | Not Started
2025-07-25 | Assurant | CEP - Portal |  |  | Implement Answer Management System | 493330 | 493335 | Development |  | Hariharan | None | None |  | Sprint 15 | 2025-07-28 | 2025-07-30 | 24 |  |  | 0 | 24 | 24 | 0 | Not Started
2025-07-25 | Assurant | CEP - Portal |  |  | Implement & Intergrate MyRequest Page for App Team | 493330 | 493336 | Development |  | Sutharsan | None | None |  | Sprint 15 | 2025-07-17 | 2025-07-18 | 12 |  |  | 0 | 12 | 12 | 0 | Not Started
2025-07-25 | Assurant | CEP - Portal |  |  | Implement & Intergrate Request Overview Page for CEP Team, to add ability for feedback loop | 493330 | 493337 | Development |  | Sutharsan | None | None |  | Sprint 15 | 2025-07-18 | 2025-07-21 | 16 |  |  | 0 | 16 | 16 | 0 | Not Started
2025-07-25 | Assurant | CEP - Portal |  |  | Integrate Questoinnaire Form Submission for CEP Team | 493330 | 493338 | Development |  | Sutharsan | None | None | 80 | Sprint 15 | 2025-07-22 | 2025-07-23 | 8 |  |  | 0 | 8 | 8 | 0 | Not Started
2025-07-25 | Assurant | CEP - Portal |  |  | Integrate Questoinnaire Form Submission for CEP Team | 493330 | 493338 | Development |  | Raj | None | None |  | Sprint 15 | 2025-07-22 | 2025-07-23 | 8 |  |  | 0 | 8 | 8 | 0 | Not Started
2025-07-25 | Assurant | CEP - Portal |  |  | Implement and Integrate Edit Questoinnaire Form Submission for CEP Team | 493330 | 493339 | Development |  | Sutharsan | None | None |  | Sprint 15 | 2025-07-24 | 2025-07-28 | 20 |  |  | 0 | 20 | 20 | 0 | Not Started
2025-07-25 | Assurant | CEP - Portal |  |  | Implement and Integrate Edit and View Questoinnaire Form Submission for App Team | 493330 | 493340 | Development |  | Sutharsan | None | None |  | Sprint 15 | 2025-07-28 | 2025-07-30 | 20 |  |  | 0 | 20 | 20 | 0 | Not Started
2025-07-25 | Assurant | CEP - Portal |  |  | Technical Support for Platform Questinarie Managment & Feedbackloop Cycle | 493330 | 493342 | Plan |  | Raj | None | None | 60 | Sprint 16 | 2025-07-31 | 2025-08-04 | 30 |  |  | 0 | 30 | 30 | 0 | Not Started
2025-07-25 | Assurant | CEP - Portal |  |  | Task Managment Approach Plab | 493330 |  | Plan |  | Sutharsan | None | None | 80 | Sprint 16 | 2025-07-31 | 2025-08-04 | 16 |  |  | 0 | 16 | 16 | 0 | Not Started