## Sheet1
Month | Client Name | Project / Workstream Name | CSP | Application / App Team | Deliverable | Work Item / Product Backlog Item | Type (Plan, Design, Dev, QA, Deploy, Document) | Acceptance Criteria | Team Member | Dependencies | Waiting On | Capacity | Sprint | Estimated Start Data | Estimated End Date | Estimated Effort (Hours) | Actual Start Date | Actual End Date | Actual Effort Hours | ETC (Estimate to Complete) | EAC (Estimate at Completion) | Variance | Status (Completed / Pending) | Remarks
2025-01-25 | Assurant | CEP Observability |  |  | Firewall Dashboard | 480309 | Build | Tunnel Status Visibility | Swetha | None | None | 40 | 2025 Q1 Sprint1 | 2025-12-31 | 2025-01-13 | 12 | 2025-01-07 | 2025-01-13 | 14 | 0 | 14 | 2 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Adding New Tiles to Dashboard Links | 480309 | Build | To redirect from General Dashboard Links | Swetha | None | None |  | 2025 Q1 Sprint1 | 2025-12-31 | 2025-01-13 | 6 | 2025-01-10 | 2025-01-14 | 6 | 0 | 6 | 0 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Summary Dashboard For Tunnel Operation Status | 480609 | Build | Standared Summary Panels | Swetha | None | None |  | 2025 Q1 Sprint1 | 2025-12-31 | 2025-01-13 | 2 | 2025-01-07 | 2025-01-13 | 3 | 0 | 3 | 1 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Terraform Module - Serviceprinciple Creation | 480629 | Dev | Azure App Registration | Swetha | TFC Workspace Access | Approval |  | 2025 Q1 Sprint1 | 2025-12-31 | 2025-01-13 | 20 | 2025-01-08 | 2025-01-15 | 21 | 0 | 21 | 1 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Grafana - NFV - Change CPU Panels for AT4 and CH3 | 481605 | Support | To update Dashboard | Swetha | None | None |  | 2025 Q1 Sprint1 | 2025-12-31 | 2025-01-13 | 1 | 2025-01-20 | 2025-01-20 | 1 | 0 | 1 | 0 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Terraform Module - Datasource Integration | 479446 | Dev | Azure & Grafana Integration | Swetha | TFC Workspace Access | None | 40 | 2025 Q1 Sprint2 | 2025-01-14 | 2025-01-27 | 12 | 2025-01-16 | 2025-01-29 | 22 | 0 | 22 | 10 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Grafana - NFV - Correct Panel visualization for Usage | 481610 | Design & Build | To update Dashboard | Swetha | None | None |  | 2025 Q1 Sprint2 | 2025-01-14 | 2025-01-27 | 6 | 2025-01-20 | 2025-01-21 | 8 | 0 | 8 | 2 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Update Global Session Maximum values for ACE Firewall Grafana Dashboards | 482103 | Update | To update Dashboard | Swetha | None | None |  | 2025 Q1 Sprint2 | 2025-01-14 | 2025-01-27 | 8 | 2025-01-21 | 2025-01-22 | 12 | 0 | 12 | 4 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Fix Cloud Health Check Dashboard - Level 3 Dashboard for the Datadog Monitors Modified | 482225 | Update | To update Dashboard | Swetha | None | None |  | 2025 Q1 Sprint2 | 2025-01-14 | 2025-01-27 | 4 | 2025-01-22 | 2025-01-22 | 5 | 0 | 5 | 1 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Grafana - NFV - Obtain the last 6 months average Network in and Out | 481607 | Support | To update threshold | Swetha | None | None |  | 2025 Q1 Sprint2 | 2025-01-14 | 2025-01-27 | 6 | 2025-01-27 | 2025-01-29 | 10 | 0 | 10 | 4 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Grafana - Query Process for NFV vm's dashboard recreation | 482653 | Design & Build | To process query for data | Swetha | None | None | 40 | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 4 | 2025-01-28 | 2025-01-28 | 4 | 0 | 4 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Grafana - NFV - Obtain the last 6 months average Network in and Out | 482999 | Support | To update threshold | Swetha | None | None |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 6 | 2025-01-28 | 2025-01-29 | 6 | 0 | 6 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Create NFV VM Detailed Dashboard recreation | 481611 | Design & Build | To recreate Dashboard | Swetha | None | None |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 18 | 2025-01-29 | 2025-02-03 | 18 | 0 | 18 | 0 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Datadog Synthetic Monitors Creation Requirement Gathering and Understanding | 482105 | Plan | Requirement Document | Swetha | None | None |  | 2025 Q1 Sprint2 | 2025-01-28 | 2025-02-10 | 2 | 2025-02-01 | 2025-02-01 | 2 | 0 | 2 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Grafana - NFV - Obtain last 6 months network average for Network Throughput Read and Write | 481608 | Update | To update threshold | Swetha | None | None |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 8 | 2025-01-28 | 2025-02-03 | 8 | 0 | 8 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Azure Monitor Datasource Integration in Grafana Using Terraform - Review | 482998 | Support | To review and modify if any | Swetha | Orchestration team | Alex |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 6 | 2025-01-29 | 2025-02-10 | 6 | 0 | 6 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Requirement gathering for Grafan config management | 483315 | Plan | Requirement Understanding | Swetha | None | None |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 4 | 2025-02-05 | 2025-02-10 | 6 | 0 | 6 | 2 | Done
2025-01-25 | Assurant | CEP Observability |  |  | To Add Additional Metrics in Co-Pilot Dashboard | 480886 | Support | Data Availability in Grafana | Thooyavan | Avaitrix & Co-pilot Team | None | 80 | 2025 Q1 Sprint1 | 2025-12-31 | 2025-01-13 | 6 | 2025-01-09 | 2025-01-10 | 6 | 0 | 6 | 0 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Discuss and Finalize AD Monitor Parameters | 480885 | Plan | To Update AD Monitors | Thooyavan | None | None |  | 2025 Q1 Sprint1 | 2025-12-31 | 2025-01-13 | 2 | 2025-01-09 | 2025-01-13 | 2 | 0 | 2 | 0 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Azure App Registration Secrets Dashboard | 477118 | Design & Build | Azure Key vault Status | Thooyavan | Grafana Support | Feature Request |  | 2025 Q1 Sprint1 | 2025-12-31 | 2025-01-13 | 32 | 2025-12-18 | 2025-01-07 | 64 | 0 | 64 | 32 | Done | Completed with Workaround
2025-01-25 | Assurant | CEP Observability |  |  | Co-pilot Data Streaming issue | 478424 | Support | Data Availability in Grafana | Thooyavan | Avaitrix & Co-pilot Team | Solution | 80 | 2025 Q1 Sprint2 | 2025-01-14 | 2025-01-27 | 12 | 2024-12-03 | 2025-01-27 | 16 | 0 | 16 | 4 | Done | Moved to next sprint as the fix is on hold
2025-01-25 | Assurant | CEP Observability |  |  | Add Azure Status to Grafana VDC dashboard | 481066 | Build | To add Azure Status | Thooyavan | None | None |  | 2025 Q1 Sprint2 | 2025-01-14 | 2025-01-27 | 24 | 2025-01-21 | 2025-01-27 | 24 | 0 | 24 | 0 | Done | Moved to next sprint as the task is pending
2025-01-25 | Assurant | CEP Observability |  |  | Azure Monitor Datasource Integration in Grafana Using Terraform - Review | 482998 | Support | To review and modify if any | Swetha | Orchestration team | Alex | 40 | 2025 Q1 Sprint4 | 2025-02-11 | 2025-02-24 | 5 | 2025-02-10 | 2025-02-24 | 12 | 0 | 12 | 7 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Azure Monitor Datasource Integration in Grafana Using Terraform - Merge Follow up | 484021 | Support | To follow up for merge from feature to develop | Swetha | Shiva | Shiva |  | 2025 Q1 Sprint4 | 2025-02-11 | 2025-02-24 | 3 | 2025-02-11 | 2025-02-17 | 7 | 0 | 7 | 4 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Troubleshoot SQL DB dashboard No Data Issue | 484416 | Troubleshooting | To find solution on authentication approach | Swetha | None | None |  | 2025 Q1 Sprint4 | 2025-02-11 | 2025-02-24 | 4 | 2025-02-18 | 2025-02-23 | 3 | 0 | 3 | -1 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Terraform Auto rotate key configuration testing for Service Principal | 483310 | Design & Test | To design and test SP key rotation in data source | Swetha | None | None |  | 2025 Q1 Sprint4 | 2025-02-11 | 2025-02-24 | 8 | 2025-02-11 | 2025-02-12 | 9 | 0 | 9 | 1 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Groups and Users Segregation for Grafana config IAM management | 483964 | Design & Build | To plan and segregate users and groups in grafana | Swetha | None | None |  | 2025 Q1 Sprint4 | 2025-02-11 | 2025-02-24 | 5 | 2025-02-11 | 2025-07-18 | 10 | 0 | 10 | 5 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Groups and Users Segregation for Grafana using Terraform - POC | 484320 | Design & Build | To build Poc code for Grafana IAM config | Swetha | None | None | 40 | 2025 Q1 Sprint5 | 2025-02-25 | 2025-03-10 | 6 | 2025-02-18 | 2025-02-27 | 8 | 0 | 8 | 2 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Design Workflow for service accounts and cloud access policies for automation | 483312 | Design & Build | To design Workflow for service accounts and cloud access policies for automation | Swetha | None | None |  | 2025 Q1 Sprint5 | 2025-02-25 | 2025-03-10 | 6 | 2025-05-03 | 2025-02-10 | 12 | 0 | 12 | 6 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Terraform Auto rotate Service account key configuration testing | 484812 | Build | To build and test key rotatio of service accounts | Swetha | None | None |  | 2025 Q1 Sprint5 | 2025-02-25 | 2025-03-10 | 10 | 2025-02-25 |  | 10 | 0 | 10 | 0 | Pending
2025-01-25 | Assurant | CEP Observability |  |  | Add zscaler Tunnel status in Grafana Network dashboard | 484886 | Build | To update tunnel info in grafana dashboard | Swetha | None | None |  | 2025 Q1 Sprint5 | 2025-02-25 | 2025-03-10 | 6 | 2025-02-28 | 2025-02-10 | 8 | 0 | 8 | 2 | Done | reviewed
2025-01-25 | Assurant | CEP Observability |  |  | Azure VDC consumption Dashboard - Panel Alignment and Design | 478651 | Design & Build | To align panels for VDC Consumption dashboard | Swetha | None | None |  | 2025 Q1 Sprint5 | 2025-02-25 | 2025-03-10 | 4 | 2025-02-26 | 2025-02-28 | 3 | 0 | 3 | -1 | Done | To be reviewed
2025-03-25 | Assurant | CEP Observability |  |  | Terraform Auto rotate Service account key configuration testing | 484812 | Build | To build and test key rotatio of service accounts | Swetha | None | None |  | 2025 Q1 Sprint6 | 2025-02-25 | 2025-03-10 | 10 | 2025-02-25 | 2025-03-11 | 14 | 0 | 14 | 4 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana - TMO Application Dashboard Requirements - Data Gathering | 486269 | Support | To gather data for TMO application dashboard | Swetha | None | None | 40 | 2025 Q1 Sprint6 | 2025-03-11 | 2025-03-24 | 5 | 2025-03-17 | 2025-03-18 | 6 | 0 | 6 | 1 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Config - Terraform Service Account Role Assignment | 485991 | Build | To build role assignment for service account | Swetha | None | None |  | 2025 Q1 Sprint6 | 2025-03-11 | 2025-03-24 | 6 | 2025-03-11 | 2025-03-14 | 9 | 0 | 9 | 3 | Done
2025-03-25 | Assurant | CEP Observability |  |  | [SCTASK1415419] Need to get Requests Exceptions/Error logs from Application insight for 2 Services | 486646 | Support | To support for bringing logs in datadog for 2 app services | Swetha | None | None |  | 2025 Q1 Sprint6 | 2025-03-11 | 2025-03-24 | 2 | 2025-03-24 | 2025-03-24 | 2 | 0 | 2 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Listing No Data Dashboards and Troubleshooting the Issue | 486261 | Build | To troubleshoot no data dashboard panels | Swetha | None | None |  | 2025 Q1 Sprint6 | 2025-03-11 | 2025-03-24 | 6 | 2025-03-17 | 2025-03-19 | 8 | 0 | 8 | 2 | Done
2025-03-25 | Assurant | CEP Observability |  |  | [SCTASK1401299] Need to get Requests Exceptions/Error logs from Application insight for Sales services - appi-mfh-sf-sales-prod-ins | 485684 | Support | Support for application team | Swetha | None | None |  | 2025 Q1 Sprint6 | 2025-03-11 | 2025-03-24 | 2 | 2025-03-11 | 2025-03-11 | 2 | 0 | 2 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Documentation on Grafana Dashboard details and Dependencies | 486263 | Build | To create document for all grafana dashboard dependencies | Swetha | None | None | 40 | 2025 Q1 Sprint7 | 2025-03-25 | 2025-04-07 | 8 | 2025-03-24 | 2025-03-28 | 8 | 0 | 8 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Config - Custom Role Permission testing for Users and Contributors with Test Account | 486597 | Design and Test | To test user and contributor role access | Swetha | None | None |  | 2025 Q1 Sprint7 | 2025-03-25 | 2025-04-07 | 12 | 2025-03-23 | 2025-03-25 | 12 | 0 | 12 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Config - Cloud Access Policy and Token key rotation Automation | 483313 | Build | To build cloud access policy and token on grafana using terraform | Swetha | None | None |  | 2025 Q1 Sprint7 | 2025-03-25 | 2025-04-07 | 14 | 2025-03-13 | 2025-03-28 | 13 | 0 | 13 | -1 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Datadog Synthetic Monitors Creation for Mainframe resources - Pricing & Approval | 482520 | Pricing | To work on pricing for monitors | Thooyavan | None | None |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 8 | 2025-01-28 | 2025-01-29 | 8 | 0 | 8 | 0 | Done
2025-01-25 | Assurant | CEP Observability |  |  | AD Monitors - Datadog Modifications | 481352 | Support | To Update AD Monitors | Thooyavan | None | None |  | 2025 Q1 Sprint2 | 2025-01-14 | 2025-01-27 | 6 | 2025-01-21 | 2025-01-21 | 4 | 0 | 4 | -2 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Update Grafana Dashboards with new AT4INET Switch Information | 480791 | Plan | To Update AT4INET | Thooyavan | None | None |  | 2025 Q1 Sprint2 | 2025-01-14 | 2025-01-27 | 4 | 2025-01-21 | 2025-01-21 | 4 | 0 | 4 | 0 | Done
2025-01-25 | Assurant | CEP Observability |  |  | Oracle Metric Dimension - Phoenix Region | 480640 | Support | Dimensions Visibility | Thooyavan | OCI Support | Solution |  | 2025 Q1 Sprint2 | 2025-01-14 | 2025-01-27 | 12 | 2025-01-07 | 2025-01-27 | 8 | 0 | 8 | -4 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Aviatrix CoPilot gateway TMO Dashboard : Summary and Standard Panel TMO Controller | 477035 | Build | Standared Summary Panels | Thooyavan | Avaitrix & Co-pilot Team | Tzahi ( Aviatrix support Team) |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 2 | 2025-01-30 | 2025-01-30 | 2 | 0 | 2 | 0 | Done | Waiting for Aviatrix New Release
2025-02-25 | Assurant | CEP Observability |  |  | Oracle Metric Dimension - Phoenix Region | 483062 | Support | Dimensions Visibility | Thooyavan | OCI Support | Rajeswari(Oracle Support team) |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 8 | 2025-01-28 |  | 8 | 0 | 8 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Aviatrix CoPilot gateway Dashboard Review | 466667 | Review | Review Dashboard | Thooyavan | Avaitrix & Co-pilot Team | None |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 2 |  |  | 2 | 0 | 2 | 0 | Done | Waiting for Aviatrix New Release
2025-02-25 | Assurant | CEP Observability |  |  | Add Azure Status to Grafana VDC dashboard | 483001 | Build | To add Azure Status | Thooyavan | None | None |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 4 | 2025-02-03 | 2025-02-03 | 4 | 0 | 4 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Datadog Synthetic Monitors Creation for Mainframe resources | 482105 | Design & Build | To create monitors | Thooyavan | None | None |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 10 | 2025-01-30 |  | 10 | 0 | 10 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Aviatrix CoPilot gateway Dashboard : Troubleshoot the Gateway and Tunnel Status Data Stream issues | 483000 | Support | To Troubleshoot | Thooyavan | None | Tzahi ( Aviatrix support Team) |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 12 | 2025-01-28 |  | 12 | 0 | 12 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Datadog Synthetic Monitors Creation for Mainframe resources - Pricing & Approval | 482520 | Plan | Pricing Approved | Thooyavan | None | None |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 2 | 2025-01-30 | 2025-01-30 | 2 | 0 | 2 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Aviatrix CoPilot gateway Dashboard for TMO Controller | 477034 | Plan | TMO Controller Status | Thooyavan | Avaitrix & Co-pilot Team | None | 80 | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 16 | 2025-01-28 | 2025-01-30 | 16 | 0 | 16 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Datadog Synthetic Monitors Creation for Mainframe resources - Requirement Understanding & Readiness | 484024 | Plan | Pricing Approved | Thooyavan | None | None |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 7 | 2025-01-30 | 2025-01-30 | 7 | 0 | 7 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | [SCTASK1375554] Enable Prometheus/OpenMetric Integrations in Datadog | 483106 | Support | Implement Open metrics integration | Thooyavan | None | None |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 4 | 2025-02-10 | 2025-02-10 | 4 | 0 | 4 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | [SCTASK1378014] Need API key read permissions to integrate github with Datadog | 483333 | Support | Implement Github and Webhook Integration | Thooyavan | None | None |  | 2025 Q1 Sprint3 | 2025-01-28 | 2025-02-10 | 4 | 2025-02-04 |  | 4 | 0 | 4 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Oracle Metric Dimension - Phoenix Region (BLOCKED) | 483062 | Support | Dimensions Visibility | Thooyavan | OCI Support | Rajeswari(Oracle Support team) | 80 | 2025 Q1 Sprint4 | 2025-02-11 | 2025-02-24 | 6 | 2025-01-28 |  | 1 | 5 | 6 | 0 | Pending
2025-02-25 | Assurant | CEP Observability |  |  | Datadog Synthetic Monitors Creation for Mainframe resources | 482105 | Design & Build | To create monitors | Thooyavan | None | None |  | 2025 Q1 Sprint4 | 2025-02-11 | 2025-02-24 | 9 | 2025-01-30 | 2025-02-13 | 13 | 0 | 13 | 4 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Aviatrix CoPilot gateway Dashboard : Troubleshoot the Gateway and Tunnel Status Data Stream issues | 483000 | Support | To Troubleshoot | Thooyavan | None | Tzahi ( Aviatrix support Team) |  | 2025 Q1 Sprint4 | 2025-02-11 | 2025-02-24 | 8 | 2025-01-28 | 2025-02-24 | 16 | 0 | 16 | 8 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Grafana IAM - RBAC Planning and Permisson Mapping | 484305 | Design & Build | Grafana IAM Configuration | Thooyavan | None | None |  | 2025 Q1 Sprint4 | 2025-02-11 | 2025-02-24 | 8 | 2025-02-14 | 2025-02-19 | 8 | 0 | 8 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | [SCTASK1378014] Need API key read permissions to integrate github with Datadog | 483333 | Support | Implement Github and Webhook Integration | Thooyavan | None | None |  | 2025 Q1 Sprint4 | 2025-02-11 | 2025-02-24 | 3.5 | 2025-02-04 | 2025-02-20 | 4 | 0 | 4 | 0.5 | Done
2025-02-25 | Assurant | CEP Observability |  |  | [SCTASK1375554] Enable Prometheus/OpenMetric Integrations in Datadog | 483106 | Support | Enable Prometheus/OpenMetric Integrations in Datadog | Thooyavan | None | None |  | 2025 Q1 Sprint4 | 2025-02-11 | 2025-02-24 | 4 | 2025-02-11 | 2025-11-02 | 4 | 0 | 4 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Azure SQL Database & Elastic Pool Usage Dashboard in Grafana | 484403 | Design & Build | Design Dashboard | Thooyavan | None | None |  | 2025 Q1 Sprint4 | 2025-02-11 | 2025-02-24 | 16 | 2025-02-19 | 2025-02-20 | 16 | 0 | 16 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Grafana IAM Approach and Role Mapping | 483939 | Plan | Design and Documentation | Thooyavan | None | None |  | 2025 Q1 Sprint4 | 2025-02-11 | 2025-02-24 | 12 | 2025-02-11 | 2025-02-22 | 12 | 0 | 12 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Aviatrix CoPilot gateway Dashboard Review | 466667 | Review | Review Dashboard | Thooyavan | Avaitrix & Co-pilot Team | None |  | 2025 Q1 Sprint5 | 2025-02-25 | 2025-03-10 | 2 | 2025-03-03 | 2025-03-03 | 2 | 0 | 2 | 0 | Done | Waiting for Aviatrix New Release
2025-02-25 | Assurant | CEP Observability |  |  | [SCTASK1389414] Add Monitoring for Hyla, ATT , Spectrum, ipsec vpn Tunnels on ATL0D01FW33P | 484400 | Support | Monitor support | Thooyavan | None | None | 80 | 2025 Q1 Sprint5 | 2025-02-25 | 2025-03-10 | 5 | 2025-02-25 | 2025-03-03 | 5 | 0 | 5 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Aviatrix CoPilot gateway Dashboard : Summary Dashboard for Prod and TMO Controller | 484809 | Summary | To review and sign-off | Thooyavan | None | None |  | 2025 Q1 Sprint5 | 2025-02-25 | 2025-03-10 | 5 | 2025-02-25 | 2025-02-27 | 5 | 0 | 5 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Grafana IAM - Documentation | 484970 | Document | To design document | Thooyavan | None | None |  | 2025 Q1 Sprint5 | 2025-02-25 | 2025-03-10 | 4 | 2025-02-27 | 2025-03-03 | 4 | 0 | 4 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Grafana IAM - Review & Validation | 484740 | Review | To review | Thooyavan | None | None |  | 2025 Q1 Sprint5 | 2025-02-25 | 2025-03-10 | 2 | 2025-02-25 | 2025-03-27 | 2 | 0 | 2 | 0 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Grafana IAM - Custom Role Creation and Mapping - Testing | 484843 | Testing | To test custom role settings and permissions | Thooyavan | None | None |  | 2025 Q1 Sprint5 | 2025-02-25 | 2025-03-10 | 12 | 2025-03-03 | 2025-03-10 | 12 | 0 | 12 | 0 | Done | Raised support case in Grafana
2025-03-25 | Assurant | CEP Observability |  |  | Grafana IAM - Dashboard Permissons and Grouping Validation - Testing | 484845 | Testing | To test Dashboard Permissons and Grouping | Thooyavan | None | None |  | 2025 Q1 Sprint6 | 2025-03-11 | 2025-03-24 | 8 | 2025-03-19 | 2025-03-24 | 9 | 0 | 9 | 1 | Done
2025-02-25 | Assurant | CEP Observability |  |  | Mainframe resources Datadog Monitor - Connecticity Troublehooting | 484819 | Troubleshooting | To roubleshoot connectivity issue | Thooyavan | None | None |  | 2025 Q1 Sprint5 | 2025-02-25 | 2025-03-10 | 2 | 2025-02-27 | 2025-03-03 | 2 | 0 | 2 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana - Azure TMO Application Dashboard | 486270 | Build | To build dashboard | Thooyavan | None | None |  | 2025 Q1 Sprint6 | 2025-03-11 | 2025-03-24 | 4 | 2025-03-18 | 2025-03-24 | 6 | 0 | 6 | 2 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana - Aws TMO Application Dashboard | 486271 | Build | To build dashboard | Thooyavan | None | None | 80 | 2025 Q1 Sprint6 | 2025-03-11 | 2025-03-24 | 4 | 2025-03-18 | 2025-03-24 | 6 | 0 | 6 | 2 | Done
2025-03-25 | Assurant | CEP Observability |  |  | [SCTASK1401785] Synthetic monitoring check and alert | 485760 | Support | [SCTASK1401785] Synthetic monitoring check and alert | Thooyavan | None | None |  | 2025 Q1 Sprint6 | 2025-03-11 | 2025-03-24 | 2 | 2025-03-11 | 2025-03-11 | 2 | 0 | 2 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | [SCTASK1413469] Request to add the OData plugin to Grafana to enable direct integration with the Citrix OData API | 486479 | Support | [[SCTASK1413469] Request to add the OData plugin | Thooyavan | None | None |  | 2025 Q1 Sprint6 | 2025-03-11 | 2025-03-24 | 4 | 2025-03-21 | 2025-03-24 | 4 | 0 | 4 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Aviatrix CoPilot gateway Dashboard : Summary Dashboard Model Environment | 485763 | Build | Aviatrix CoPilot gateway Dashboard : Summary Dashboard Model Environment | Thooyavan | None | None |  | 2025 Q1 Sprint6 | 2025-03-11 | 2025-03-24 | 6 | 2025-03-11 | 2025-03-20 | 6 | 0 | 6 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Aviatrix CoPilot gateway Dashboard : Detailed Dashboard Model Environment | 485764 | Build | Aviatrix CoPilot gateway Dashboard : Detailed Dashboard Model Environment | Thooyavan | None | None |  | 2025 Q1 Sprint6 | 2025-03-11 | 2025-03-24 | 6 | 2025-03-12 | 2025-03-20 | 6 | 0 | 6 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana IAM - Prepare Action and Scope for User and Contributor - Testing | 485985 | Build | Grafana IAM - Prepare Action and Scope for User and Contributor - Testing | Thooyavan | None | None |  | 2025 Q1 Sprint6 | 2025-03-11 | 2025-03-24 | 12 | 2025-03-20 | 2024-03-24 | 12 | 0 | 12 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Review the DNS dashboard | 484622 | Review | Review the DNS dashboard | Thooyavan | None | Trying to find a workaround solution |  | 2025 Q1 Sprint7 | 2025-03-25 | 2025-04-07 | 12 | 2025-02-25 |  | 4 | 8 | 12 | 0 | Pending
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Config - Teams and Roles Creation In Terraform | 485890 | Build | Grafana Config - Teams and Roles Creation In Terraform | Thooyavan | None | None |  | 2025 Q1 Sprint7 | 2025-03-25 | 2025-04-07 | 18 | 2025-03-12 |  | 18 | 0 | 18 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Config - Role Assignment to Teams In Terraform | 485891 | Build | Grafana Config - Role Assignment to Teams In Terraform | Thooyavan | None | None | 80 | 2025 Q1 Sprint7 | 2025-03-25 | 2025-04-07 | 15 |  |  | 15 | 0 | 15 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Mainframe resources Datadog Monitor - Troubleshoot and Fix Connectivity Issues | 485762 | Troubleshooting | Mainframe resources Datadog Monitor - Troubleshoot and Fix Connectivity Issues | Thooyavan | None | None |  | 2025 Q1 Sprint7 | 2025-03-25 | 2025-04-07 | 8 |  |  | 8 | 0 | 8 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana - TMO Dashboard Extrahop Metrics - API Gathering & Panel Creation | 486670 | Data gather and build | Extrahop metrics data gather and panel creation | Thooyavan | None | None |  | 2025 Q1 Sprint7 | 2025-03-25 | 2025-04-07 | 16 | 2025-03-26 | 2025-03-28 | 16 | 0 | 16 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana - TMO Dashboard - Panel Modifcations and Validation | 486671 | Validation | Validate dashboard | Thooyavan | None | None |  | 2025 Q1 Sprint7 | 2025-03-25 | 2025-04-07 | 6 | 2025-03-28 | 2025-04-01 | 6 | 0 | 6 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | [SCTASK1412533] CDW ThousandEyes Read Only Access | 486417 | support | support for read only access | Thooyavan | None | None |  | 2025 Q1 Sprint7 | 2025-03-25 | 2025-04-07 | 4 | 2025-03-20 | 2025-03-27 | 4 | 0 | 4 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Dashboard - Modify Database Dashboard SQL metrics | 487013 | support | dashboard modification | Thooyavan | None | None |  | 2025 Q1 Sprint7 | 2025-03-25 | 2025-04-07 | 4 | 2025-04-01 | 2025-04-01 | 4 | 0 | 4 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Config - Cloud Access Policy Role Assignment Automation | 486014 | Build | To build role assignment for cloud access policy | Thooyavan | None | None |  | 2025 Q1 Sprint7 | 2025-03-25 | 2025-04-07 | 6 |  |  | 6 | 0 | 6 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Dashboard for Mainframe Synthetic Monitors | 482097 | Design & Build | To create dashboard | Thooyavan | None | None |  | 2025 Q1 Sprint7 | 2025-03-25 | 2025-04-07 | 10 |  |  | 10 | 0 | 10 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Config - Teams and Roles Creation In Terraform | 485890 | Build | Grafana Config - Teams and Roles Creation In Terraform | Thooyavan | None | None |  | 2025 Q2 Sprint1 | 2025-03-25 | 2025-04-07 | 18 | 2025-12-03 | 2025-04-16 | 18 | 0 | 18 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Config - Role Assignment to Teams In Terraform | 485891 | Build | Grafana Config - Role Assignment to Teams In Terraform | Thooyavan | None | None | 80 | 2025 Q2 Sprint1 | 2025-03-25 | 2025-04-07 | 15 | 2025-04-09 | 2025-04-16 | 15 | 0 | 15 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Dashaboards show No data | 486238 | Build | To troubleshoot no data dashboards | Thooyavan | None | None |  | 2025 Q2 Sprint1 | 2025-03-25 | 2025-04-07 | 6 | 2025-04-15 | 2025-04-21 | 8 | 0 | 8 | 2 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Config - Cloud Access Policy Role Assignment Automation | 486014 | Build | To build role assignment for cloud access policy | Thooyavan | None | None |  | 2025 Q2 Sprint1 | 2025-03-25 | 2025-04-07 | 6 | 2025-04-16 | 2025-04-21 | 16 | 0 | 16 | 10 | Done
2025-03-25 | Assurant | CEP Observability |  |  | SCTASK1428963 ¦ We need to setup 7 synthetic monitors in Datadog | 487376 | sctask | to setup 7 synthetic monitors in Datadog | Thooyavan | None | None |  | 2025 Q2 Sprint1 | 2025-03-25 | 2025-04-07 | 6 | 2025-04-16 | 2025-04-21 | 6 | 0 | 6 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Dashboard - Validate All the Dashboards (Thooyavan) - Q2 Sprint -1 | 487397 | Validate | validate dashboards | Thooyavan | None | None |  | 2025 Q2 Sprint1 | 2025-03-25 | 2025-04-07 | 6 | 2025-04-13 | 2025-04-15 | 6 | 0 | 6 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | [Apr 18] Grafana - TMO Dashboard Extrahop Metrics - AWS | 487400 | Build | to integrate Extrahop metrics by gathering data via API and visualizing it in dedicated panels | Thooyavan | None | None |  | 2025 Q2 Sprint1 | 2025-03-25 | 2025-04-07 | 6 | 2025-04-16 | 2025-04-21 | 6 | 0 | 6 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana - TMO Dashboard - Modify Dashboard based on Network team feedback | 487399 | Build | updating and validating existing panels on the TMO Grafana dashboard | Thooyavan | None | None |  | 2025 Q2 Sprint1 | 2025-03-25 | 2025-04-07 | 6 | 2025-04-13 | 2025-04-15 | 6 | 0 | 6 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Datadog - Default Monitors Modifications | 487467 | modifications | modify dashboards | Thooyavan | None | None |  | 2025 Q2 Sprint1 | 2025-03-25 | 2025-04-07 | 10 | 2025-04-18 | 2025-04-21 | 8 | 0 | 8 | -2 | Done
2025-03-25 | Assurant | CEP Observability |  |  | SCTASK1431771 ¦ Intergration of Datadog for Enterprise Analytics Portal | 487533 | integration | sctask | Thooyavan | None | None |  | 2025 Q2 Sprint1 | 2025-03-25 | 2025-04-07 | 10 | 2025-04-18 | 2025-04-21 | 12 | 0 | 12 | 2 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana - Delete AWS Accounts and Scrape Job Integration | 487988 | deletion | deletion | Thooyavan | None | None |  | 2025 Q2 Sprint1 | 2025-03-25 | 2025-04-07 | 2 | 2025-04-18 | 2025-04-21 | 2 | 0 | 2 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Datadog - Dcoument Permisson Restriction for Monitors | 487990 | Documentation | documentation | Thooyavan | None | None |  | 2025 Q2 Sprint1 | 2025-03-25 | 2025-04-07 | 2 | 2025-04-19 | 2025-04-21 | 2 | 0 | 2 | 0 | Done
2025-03-25 | Assurant | CEP Observability |  |  | Grafana Dashboard for Mainframe Synthetic Monitors | 482097 | Design & Build | To create dashboard | Thooyavan | None | None |  | 2025 Q2 Sprint1 | 2025-03-25 | 2025-04-07 | 10 | 2025-04-18 | 2025-04-21 | 12 | 0 | 12 | 2 | Done
2025-04-25 | Assurant | CEP Observability |  |  | Grafana IAM - SAML Assertion Plan and Custom Role Integration | 487274 | Development |  | Thooyavan | None | None | 80 | 2025 Q2 Sprint2 | 2025-04-08 | 2025-04-21 | 12 | 2025-04-22 |  | 3 | 9 | 12 | 0 | pending
2025-04-25 | Assurant | CEP Observability |  |  | [Hold]Review the DNS dashboard | 484622 | Build |  | Thooyavan | None | None |  | 2025 Q2 Sprint2 | 2025-04-08 | 2025-04-21 | 12 | 2025-04-22 |  | 4 | 8 | 12 | 0 | pending
2025-04-25 | Assurant | CEP Observability |  |  | Grafana Dashboard - Document Dashboard Dependencies for All Dashboards | 487223 | Documentation | documentation | Thooyavan | None | None |  | 2025 Q2 Sprint2 | 2025-04-08 | 2025-04-21 | 6 | 2025-04-21 | 2025-04-22 | 6 | 0 | 6 | 0 | Done
2025-04-25 | Assurant | CEP Observability |  |  | Mainframe resources Datadog Monitor - Troubleshoot and Fix Connectivity Issues | 485762 | Troubleshooting | troubleshoot | Thooyavan | None | None |  | 2025 Q2 Sprint2 | 2025-04-08 | 2025-04-21 | 6 |  |  | 0 | 6 | 6 | 0 | New
2025-04-25 | Assurant | CEP Observability |  |  | Datadog - Update Service Design Pages | 488067 | update | update design page for datadog | Thooyavan | None | None |  | 2025 Q2 Sprint2 | 2025-04-08 | 2025-04-21 | 12 |  |  | 0 | 12 | 12 | 0 | New
2025-04-25 | Assurant | CEP Observability |  |  | SCTASK1440842 ¦ My team is deploying the new nutanix servers to ATL4 and want to make sure they are in logic monitor | 488205 | sctask | sctask | Thooyavan | None | None |  | 2025 Q2 Sprint2 | 2025-04-08 | 2025-04-21 | 4 |  |  | 0 | 4 | 4 | 0 | New
2025-04-25 | Assurant | CEP Observability |  |  | Datadog - Followup with Users for Permisson Restrictions | 487992 | follow up | follow up | Thooyavan | None | None |  | 2025 Q2 Sprint2 | 2025-04-08 | 2025-04-21 | 12 | 2025-04-22 |  | 4 | 4 | 8 | -4 | pending
2025-04-25 | Assurant | CEP Observability |  |  | Grafana Dashboard - Validate All the Dashboards (Thooyavan) - Q2 Sprint -2 | 488215 | validation | validation | Thooyavan | None | None |  | 2025 Q2 Sprint2 | 2025-04-08 | 2025-04-21 | 4 |  |  | 0 | 4 | 4 | 0 | New