## orchestration-details
Month | Client Name | Project / Workstream Name | CSP | Work Item / Product Backlog Item | Type | Target EPIC | Feature | Deliverable | Team Member | Status (Completed / Pending) | Parent | Sprint | Estimated Effort (Hours) | Actual Effort Hours | ETC (Estimate to Complete) | EAC (Estimate at Completion) | Variance | Type (Plan, Design, Dev, QA, Deploy, Document) | Acceptance Criteria | Capacity | Dependencies | Waiting On | Remarks
2025-01-25 | Assurant | CEP orchestration | AWS | 480363 | Product Backlog Item | Platform PROD Readiness |  | AWS IAM - PIM Integration - implementation for existing users | Senthil | Done |  | 2025 Q1 Sprint1 | 6 | 9 | 1 | 10 | 4 | Deploy | SignOff by CEP leads | 80 | Oscar Mandarano | IDM team
2025-01-25 | Assurant | CEP orchestration | AWS | 471515 | Product Backlog Item | Platform PROD Readiness |  | RBAC and AD Groups for AWS | Senthil | Done |  | 2025 Q1 Sprint2 | 20 | 4 | 0 | 4 | -16 | Design | POC Completion | 80 | Miguel Arrue
2025-01-25 | Assurant | CEP orchestration | AWS | 472912 | Product Backlog Item | AIZ Labs Modules |  | EFS Module Development and Code updates | Aravindan | Done |  | 2025 Q1 Sprint2 | 24 | 8 | 0 | 8 | -16 | Dev | Peer review and Sign off | 80
2025-01-25 | Assurant | CEP orchestration | AWS | 472930 | Product Backlog Item | Module Enhancement |  | KMS Features for different services usage pattern | Pavan | Moved To backlog |  | 2025 Q1 Sprint2 | 8 | 0 | 0 | 0 | -8 | Design | Design Document
2025-01-25 | Assurant | CEP orchestration | AWS | 475061 | Product Backlog Item | Platform PROD Readiness |  | TMO MaxValue DR on AWS : Integration testing plan and documentation | Senthil | Done |  | 2025 Q1 Sprint2 | 8 | 4 | 0 | 4 | -4 | Design | Design Review
2025-01-25 | Assurant | CEP orchestration | AWS | 481320 | Product Backlog Item | Platform PROD Readiness |  | TMO MaxValue DR on AWS : Integration testing execution | Senthil | Done |  | 2025 Q1 Sprint2 | 16 | 12 | 0 | 12 | -4 | Deploy | Demo
2025-01-25 | Assurant | CEP orchestration | AWS | 477342 | Product Backlog Item | Platform PROD Readiness |  | AWS ACM integration with KeyFactor | Pavan | Pending |  | 2025 Q1 Sprint1 | 5 | 0 | 0 | 0 | -5 | Deploy | ACM Testing |  | Security team
2025-01-25 | Assurant | CEP orchestration | Azure | 479166 | Product Backlog Item | Azure 4.X |  | P1- Module 4.x module upgrade- -azurerm-sql-failover-group-cep | Senthil | Done |  | 2025 Q1 Sprint2 | 12 | 2 | 0 | 2 | -10 | Dev | PR for review
2025-01-25 | Assurant | CEP orchestration | AWS | 479456 | Product Backlog Item | AIZ Labs Modules |  | AWS Aurora cluster 0.5 :Review and Approve Design Document | Senthil | Done |  | 2025 Q1 Sprint1 | 8 | 6 | 0 | 6 | -2 | Design | Design Review
2025-01-25 | Assurant | CEP orchestration | AWS | 480267 | Product Backlog Item | AIZ Labs Modules |  | EKS External DNS Evaluation using Infoblox | Sundaram | Done |  | 2025 Q1 Sprint1 | 12 | 10 | 0 | 10 | -2 | Design | Design Review | 80
2025-01-25 | Assurant | CEP orchestration | AWS | 480372 | Product Backlog Item | AIZ Labs Modules |  | EKS Module Feature development and Review - EKS Auth Feature | Sundaram | Done |  | 2025 Q1 Sprint2 | 16 | 2 | 0 | 2 | -14 | Dev | Peer review and Sign off | 80
2025-01-25 | Assurant | CEP orchestration | AWS | 480373 | Product Backlog Item | Platform PROD Readiness |  | AWS Accounts - Datadog Integration and validation | Senthil | Done |  | 2025 Q1 Sprint1 | 16 | 14 | 0 | 14 | -2 | Deploy | Integration validation
2025-01-25 | Assurant | CEP orchestration | AWS | 480627 | Product Backlog Item | Module Enhancement |  | Design for Cloudfront policy in S3 Module | Sundaram | Done |  | 2025 Q1 Sprint2 | 4 | 1 | 0 | 1 | -3 | Design | Design Review
2025-01-25 | Assurant | CEP orchestration | AWS | 480628 | Product Backlog Item | Module Enhancement |  | Design document update for Spoke services for the design diagrams | Senthil | Done |  | 2025 Q1 Sprint2 | 12 | 2 | 0 | 2 | -10 | Document | Documentation
2025-01-25 | Assurant | CEP orchestration | AWS | 480633 | Product Backlog Item | Module Enhancement |  | S3 cross account replication feature testing with the module | Sundaram | Done |  | 2025 Q1 Sprint2 | 16 | 2 | 0 | 2 | -14 | Dev | Peer review and Sign off
2025-01-25 | Assurant | CEP orchestration | AWS | 480649 | Product Backlog Item | Module Enhancement |  | Design Documentation update for Cloudfront usage pattern with static web hosting configuration | Sundaram | Done |  | 2025 Q1 Sprint2 | 4 | 1 | 0 | 1 | -3 | Design | Documentation
2025-01-25 | Assurant | CEP orchestration | AWS | 481606 | Product Backlog Item | TMO MV Modules |  | PR Review comments Incorporation 2 for RDS | Sundaram | Done |  | 2025 Q1 Sprint2 | 8 | 4 | 0 | 4 | -4 | Dev | Module release
2025-01-25 | Assurant | CEP orchestration | AWS | 480365 | Product Backlog Item | AIZ Labs Modules |  | Module update and Release of Cloudfront | Sundaram | Done |  | 2025 Q1 Sprint1 | 12 | 16 | 0 | 16 | 4 | Dev | Module release
2025-01-25 | Assurant | CEP orchestration | AWS | 480366 | Product Backlog Item | TMO MV Modules |  | Module update and Release of ALB | Sundaram | Done |  | 2025 Q1 Sprint1 | 10 | 16 | 0 | 16 | 6 | Dev | Module release
2025-01-25 | Assurant | CEP orchestration | AWS | 480367 | Product Backlog Item | TMO MV Modules |  | Module update and Release of NLB | Sundaram | Done |  | 2025 Q1 Sprint1 | 10 | 12 | 0 | 12 | 2 | Dev | Module release
2025-01-25 | Assurant | CEP orchestration | AWS | 480368 | Product Backlog Item | TMO MV Modules |  | Module update and Release of S3 | Sundaram | Done |  | 2025 Q1 Sprint1 | 8 | 20 | 0 | 20 | 12 | Dev | Module release
2025-01-25 | Assurant | CEP orchestration | AWS | 480369 | Product Backlog Item | TMO MV Modules |  | Module update and Release of ECR | Sundaram | Done |  | 2025 Q1 Sprint1 | 8 | 8 | 0 | 8 | 0 | Dev | Module release |  | Alex, Eric, Shad
2025-01-25 | Assurant | CEP orchestration | AWS | 480370 | Product Backlog Item | TMO MV Modules |  | Module update and Release of RDS | Sundaram | Done |  | 2025 Q1 Sprint1 | 12 | 16 | 0 | 16 | 4 | Dev | Module release |  | Alex, Eric, Shad
2025-01-25 | Assurant | CEP orchestration | AWS | 480371 | Product Backlog Item | TMO MV Modules |  | PR Review comments Incorporation for ECS | Sundaram | Done |  | 2025 Q1 Sprint2 | 8 | 2 | 0 | 2 | -6 | Dev | Module release |  | Alex, Eric, Shad
2025-01-25 | Assurant | CEP orchestration | AWS | 479455 | Product Backlog Item | AIZ Labs Modules |  | AWS Aurora cluster 0.5 Module Development | Vimal | Done |  | 2025 Q1 Sprint2 | 30 | 24 | 0 | 24 | -6 | Dev | Module release | 20
| Assurant | CEP orchestration | AWS | 479452 | Feature | AIZ Labs Modules | AWS Aurora cluster 0.5 |  | Senthil Nathan <senthil.nathan@assurant.com> | New | 481210 | GT.ICS-Cloud Planning\2025\2025 Q1 | 0 |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 479453 | Product Backlog Item | AIZ Labs Modules |  | AWS Aurora cluster 0.5 :CreateDesign Document | Vimal Gupta <vimal.gupta@assurant.com> | Done | 479452 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-3 | 8 | 8 |  | 8 | 0 |  |  | 20
| Assurant | CEP orchestration | AWS | 479455 | Product Backlog Item | AIZ Labs Modules |  | AWS Aurora cluster 0.5: Coding | Vimal | Done | 479452 | 2025 Q1 Sprint2 | 42 | 42 |  | 42 | 0
| Assurant | CEP orchestration | AWS | 479456 | Product Backlog Item | AIZ Labs Modules |  | AWS Aurora cluster 0.5 :Review and Approve Design Document | Senthil Nathan <senthil.nathan@assurant.com> | Done | 479452 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-3 | 3 | 3 | 0 | 3 | 0 |  |  | 80
| Assurant | CEP orchestration | AWS | 479457 | Product Backlog Item | AIZ Labs Modules |  | AWS Aurora cluster 0.5: Testing | Vimal | Done | 479452 | 2025 Q1 Sprint2 | 0.5 | 0.5 |  | 0.5 | 0
| Assurant | CEP orchestration | AWS | 479458 | Product Backlog Item | AIZ Labs Modules |  | AWS Aurora cluster 0.5: Design Document update | Vimal Gupta <vimal.gupta@assurant.com> | Done | 479452 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-3 | 5 | 6 |  | 6 | 1
| Assurant | CEP orchestration | AWS | 479459 | Product Backlog Item | AIZ Labs Modules |  | AWS Aurora cluster 0.5 :Update Decision Matrix | Vimal Gupta <vimal.gupta@assurant.com> | Done | 479452 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-3 | 2 | 2 |  | 2 | 0
| Assurant | CEP orchestration | AWS | 483299 | Product Backlog Item | AIZ Labs Modules |  | AWS Aurora cluster 0.5: PR feedback incorporation | Vimal Gupta <vimal.gupta@assurant.com> | Done | 479452 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-3 | 12 | 12 |  | 12 | 0
| Assurant | CEP orchestration | AWS | 483574 | Product Backlog Item | AIZ Labs Modules |  | AWS Aurora cluster 0.5 : PR review | Senthil Nathan <senthil.nathan@assurant.com> | Done | 479452 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-3 | 6 | 8 |  | 8 | 2
| Assurant | CEP orchestration | AWS | 483750 | Product Backlog Item | AIZ Labs Modules |  | AWS Aurora cluster 0.5 : PR review | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 479452 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-3 | 6 | 5 | 0 | 5 | -1 |  |  | 80
| Assurant | CEP orchestration | AWS | 481211 | Feature | Platform Enhancement | Tagging Standard at Resource Level - Review |  | Senthil Nathan <senthil.nathan@assurant.com> | New | 481210 | GT.ICS-Cloud Planning\2025\2025 Q2 | 0 |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 481219 | Product Backlog Item | Platform Enhancement |  | Tagging Standard at Resource Level :Update Decision Matrix | Senthil Nathan <senthil.nathan@assurant.com> | New | 481211 | GT.ICS-Cloud Planning\2025\2025 Q2 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 481226 | Product Backlog Item | Platform Enhancement |  | Tagging Standard at Resource Level: Module updates | Senthil Nathan <senthil.nathan@assurant.com> | New | 481211 | GT.ICS-Cloud Planning\2025\2025 Q2 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 481229 | Product Backlog Item | Platform Enhancement |  | Tagging Standard at Resource Level : Design Document and Metadata review | Senthil Nathan <senthil.nathan@assurant.com> | New | 481211 | GT.ICS-Cloud Planning\2025\2025 Q2 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 481212 | Feature | Platform Enhancement | Security Hub Implementation for AWS |  | Senthil Nathan <senthil.nathan@assurant.com> | New | 481210 | GT.ICS-Cloud Planning\2025\2025 Q2 | 0 |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 481213 | Product Backlog Item | Platform Enhancement |  | Security Hub Implementation for AWS :Review and Approve Design Document | Senthil Nathan <senthil.nathan@assurant.com> | New | 481212 | GT.ICS-Cloud Planning\2025\2025 Q2 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 481214 | Product Backlog Item | Platform Enhancement |  | Security Hub Implementation for AWS:Review and Approve Acceptance Criteria | Senthil Nathan <senthil.nathan@assurant.com> | New | 481212 | GT.ICS-Cloud Planning\2025\2025 Q2 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 481217 | Product Backlog Item | Platform Enhancement |  | Security Hub Implementation for AWS: Testing | Senthil Nathan <senthil.nathan@assurant.com> | New | 481212 | GT.ICS-Cloud Planning\2025\2025 Q2 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 481224 | Product Backlog Item | Platform Enhancement |  | Security Hub Implementation for AWS: Coding | Senthil Nathan <senthil.nathan@assurant.com> | New | 481212 | GT.ICS-Cloud Planning\2025\2025 Q2 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 481225 | Product Backlog Item | Platform Enhancement |  | Security Hub Implementation for AWS :CreateDesign Document | Senthil Nathan <senthil.nathan@assurant.com> | New | 481212 | GT.ICS-Cloud Planning\2025\2025 Q2 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 481231 | Product Backlog Item | Platform Enhancement |  | Security Hub Implementation for AWS : Implementation | Senthil Nathan <senthil.nathan@assurant.com> | New | 481212 | GT.ICS-Cloud Planning\2025\2025 Q2 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 481234 | Feature | Platform Prod Readiness | AWS PIM Integration |  | Senthil Nathan <senthil.nathan@assurant.com> | New | 481210 | GT.ICS-Cloud Planning\2025\2025 Q1 | 0 |  | 0 | 0 | 0
| Assurant | CEP orchestration | AWS | 481243 | Product Backlog Item | Platform Prod Readiness |  | AWS PIM Integration: Testing | Senthil Nathan <senthil.nathan@assurant.com> | Done | 481234 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-3 | 4 | 4 | 0 | 4 | 0
| Assurant | CEP orchestration | AWS | 481244 | Product Backlog Item | Platform Prod Readiness |  | AWS PIM Integration: Existing user migration | Senthil Nathan <senthil.nathan@assurant.com> | Done | 481234 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-3 | 8 | 8 | 0 | 8 | 0
|  |  |  | 481245 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS PIM Integration : Disable Non PIM accounts | Senthil Nathan <senthil.nathan@assurant.com> | Done | 481234 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 4 | 8 | 4
|  |  |  | 481246 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS PIM Integration : PIM Usage documentation | Senthil Nathan <senthil.nathan@assurant.com> | Done | 481234 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 4 | 0 | 4
| Assurant | CEP orchestration | AWS | 481277 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS PIM Integration: Sign-off | Senthil Nathan <senthil.nathan@assurant.com> | New | 481234 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 2 | 0 | 2 | 2 | 0
| Assurant | CEP orchestration | AWS | 484818 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Alerting Automation: SailPoint requests for AWS groups must be restricted to PIM accounts | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | In Progress | 481234 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 12 | 6 | 6 | 12 | 0
|  |  |  | 484850 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS PIM Integration : Disable Non PIM accounts - Request Team | Senthil Nathan <senthil.nathan@assurant.com> | Done | 481234 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 4 | 0 | 4
|  |  |  | 469781 | Product Backlog Item | AWS; AWS Spoke Services |  | Resource Level IAM - Sailpoint Connector POC - Troubleshoot issues | Pavan Kumar <pavan.x.kumar@assurant.com> | Removed | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4
|  |  |  | 469782 | Product Backlog Item | AWS; AWS Spoke Services |  | Resource Level IAM - Sailpoint Connector POC - Cross Account IAM Role provisioning | Pavan Kumar <pavan.x.kumar@assurant.com> | Removed | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4
|  |  |  | 481250 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Resource Level IAM :Review and Approve Design Document | Senthil Nathan <senthil.nathan@assurant.com> | New | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8
|  |  |  | 481259 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Resource Level IAM :CreateDesign Document | Senthil Nathan <senthil.nathan@assurant.com> | New | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 4
|  |  |  | 481270 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Resource Level IAM: Testing | Senthil Nathan <senthil.nathan@assurant.com> | New | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-7 | 16 | [6 empty] | 80
|  |  |  | 481286 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Resource Level IAM :Update Decision Matrix | Senthil Nathan <senthil.nathan@assurant.com> | New | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 2
|  |  |  | 481298 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Resource Level IAM: CFN for Identity provider | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 10 | 0 | 0
| Assurant | CEP orchestration | AWS | 483572 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Okta group automation - Dev prepearation for Spoke services | Aravindan Renganathan <aravindan.renganathan@assurant.com> | Done | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 16 | 16 | 0 | 16 | 0
|  |  |  | 483944 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | OKTA Integration and Group provisioning Evaluation | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 481235 | GT.ICS-Cloud Planning\2025\2025 Q4\2025 Q4 Sprint-4 | 12 | 8 | 0 |  |  |  |  | 80
|  |  |  | 483948 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Resource Level IAM: Terraform for Group Creation and Role creation | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 16 | 8 | 0
|  |  |  | 484814 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | RDS-Data Plane access | Aravindan Renganathan <aravindan.renganathan@assurant.com> | Done | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 16 | 16 | 0
|  |  |  | 484817 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | RBAC for AWS Services : S3, RDS | Aravindan Renganathan <aravindan.renganathan@assurant.com> | In Progress | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 16 | 8 | 8
| Assurant | CEP orchestration | AWS | 485518 | Task | AWS; AWS Spoke Services; Platform Prod Readiness |  |  | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 484817 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 484824 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Resource Level IAM: Testing Group Creation and Role creation using Model Okta Application via Terraform | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | In Progress | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 12 | 8 | 4 | 12 | 0
| Assurant | CEP orchestration | AWS | 485534 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS RDS RBAC for Data plane access Design | Senthil Nathan <senthil.nathan@assurant.com> | New | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8 |  |  | 0 | -8
| Assurant | CEP orchestration | AWS | 485774 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Azure Entra and AWS Managed AD sync POC | Pavan Kumar <pavan.x.kumar@assurant.com> | In Progress | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 16 |  |  | 0 | -16
| Assurant | CEP orchestration | AWS | 485775 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Azure Entra and AWS Managed AD sync - Validation | Senthil Nathan <senthil.nathan@assurant.com> | Done | 481235 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 10 | 12 | 0 | 12 | 2
| Assurant | CEP orchestration | AWS | 481280 | Product Backlog Item | AWS; AWS Platform; Platform Enhancement |  | TFC Workload Identity implementation: Role creation automation implementation | Sundaram Diraviam <sundaram.diraviam@assurant.com> | New | 481236 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 6 |  | 10 | 10 | 4
| Assurant | CEP orchestration | AWS | 481285 | Product Backlog Item | AWS; AWS Platform; Platform Enhancement |  | TFC Workload Identity implementation: Testing | Sundaram Diraviam <sundaram.diraviam@assurant.com> | New | 481236 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8 | 0 | 8 | 8 | 0
| Assurant | CEP orchestration | AWS | 481301 | Product Backlog Item | AIZ Labs Modules; AWS; AWS Spoke Services |  | EKS Enhancements : Infoblox Integration and EKS API Auth Config - PR comments incorporation 1 | Sundaram Diraviam <sundaram.diraviam@assurant.com> | Done | 481241 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 6 | 6 | 0 | 6 | 0
| Assurant | CEP orchestration | AWS | 485024 | Product Backlog Item | AIZ Labs Modules; AWS; Platform Prod Readiness |  | Infoblox webhook - Debug ingress source sync issue | Sundaram Diraviam <sundaram.diraviam@assurant.com> | Done | 481241 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 16 | 16 | 0 | 16 | 0
| Assurant | CEP orchestration | AWS | 482753 | Product Backlog Item | AWS; AWS Platform; Platform Enhancement |  | AWS Service Linked Role Enablement : Implementation | Sundaram Diraviam <sundaram.diraviam@assurant.com> | New | 481242 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8 | 0 | 8 | 8 | 0
| Assurant | CEP orchestration | AWS | 482523 | Product Backlog Item | Assurant Labs; AWS; Feature Request |  | [Feb 10] [SCTASK1372043] AWS module Elasticache - PR comments incorporation 1 | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 482632 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 25 | 25 | 0 | 25 | 0
| Assurant | CEP orchestration | AWS | 482527 | Task | Assurant Labs; AWS; Feature Request |  |  | Eric Jackson <eric.jackson1@assurant.com> | To Do | 482523 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 482528 | Task | Assurant Labs; AWS; Feature Request |  |  | Eric Jackson <eric.jackson1@assurant.com> | To Do | 482523 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 482529 | Task | Assurant Labs; AWS; Feature Request |  |  | Shad Timm <shad.timm@assurant.com> | To Do | 482523 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 482530 | Task | Assurant Labs; AWS; Feature Request |  |  | Eric Jackson <eric.jackson1@assurant.com> | To Do | 482523 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 484950 | Product Backlog Item | AWS; Feature Request; MaxValue AWS |  | [SCTASK1396167] Module for AWS Secrets Manager | Aravindan Renganathan <aravindan.renganathan@assurant.com> | In Progress | 482632 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 12 | 8 | 4 | 12 | 0
| Assurant | CEP orchestration | AWS | 484952 | Task | AWS; Feature Request; MaxValue AWS |  |  | Aravindan Renganathan <aravindan.renganathan@assurant.com> | To Do | 484950 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 484953 | Task | AWS; Feature Request; MaxValue AWS |  |  | Robert Colbert <robert.colbert@ASSURANT.COM> | To Do | 484950 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 484954 | Task | AWS; Feature Request; MaxValue AWS |  |  | Robert Colbert <robert.colbert@ASSURANT.COM> | To Do | 484950 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 484955 | Task | AWS; Feature Request; MaxValue AWS |  |  | Aravindan Renganathan <aravindan.renganathan@assurant.com> | To Do | 484950 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 |  |  |  | 0 | 0
|  |  |  | 482755 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Review Gurucul Implementation : Review for Cloudtrail Logs | Senthil Nathan <senthil.nathan@assurant.com> | New | 482730 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 6
| Assurant | CEP orchestration | AWS | 482501 | Product Backlog Item | AWS; AWS Platform; AWS Spoke Services; Platform Prod Readiness |  | Datadog - AWS Config Integration for resource tracking | Aravindan Renganathan <aravindan.renganathan@assurant.com> | New | 482731 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 6 | 0 | 6 | 6 | 0
| Assurant | CEP orchestration | AWS | 482756 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Review Datadog Integration : Account Integration | Aravindan Renganathan <aravindan.renganathan@assurant.com> | New | 482731 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 4 | 0 | 0 | 0 | -4 |  |  | 80
|  |  |  | 482757 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Review Datadog Integration : Log Ingestion for services | Aravindan Renganathan <aravindan.renganathan@assurant.com> | New | 482731 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 4 | 0 | 0 |  |  |  |  | 80
| Assurant | CEP orchestration | AWS | 484815 | Product Backlog Item |  |  | Datadog Monitor Creation- EKS | Aravindan Renganathan <aravindan.renganathan@assurant.com> | Done | 482731 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 12 |  | 0 | 0 | -12
|  |  |  | 484816 | Product Backlog Item |  |  | Datadog Monitor Creation- ECS | Aravindan Renganathan <aravindan.renganathan@assurant.com> | Done | 482731 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 12 | 12 | 0
| Assurant | CEP orchestration | AWS | 482758 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS - Default Monitor provisioning : Metrics selection for AWS services | Vimal Gupta <vimal.gupta@assurant.com> | Committed | 482732 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 14 |  |  | 0 | -14
| Assurant | CEP orchestration | AWS | 482759 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | [BLOCKED] AWS - Default Monitor provisioning: Development | Vimal Gupta <vimal.gupta@assurant.com> | Committed | 482732 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 19 |  |  | 0 | -19
| Assurant | CEP orchestration | AWS | 482760 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS - Default Monitor provisioning : PR Review | Vimal Gupta <vimal.gupta@assurant.com> | New | 482732 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8 |  |  | 0 | -8
| Assurant | CEP orchestration | AWS | 484401 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS - Default Monitor provisioning : Identify Metrics & update Design Documents of Modules | Senthil Nathan <senthil.nathan@assurant.com> | Done | 482732 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 10 |  |  | 0 | -10
|  |  |  | 484810 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS - Default Monitor provisioning : Update terraform datadog monitor metric module for AWS support | Vimal Gupta <vimal.gupta@assurant.com> | Done | 482732 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 5.5 | [6 empty] | 80
|  |  |  | 485834 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS - Default Monitor provisioning : Update terraform datadog monitor metric module for AWS support for metrics which does not start with aws | Vimal Gupta <vimal.gupta@assurant.com> | Committed | 482732 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 3
| Assurant | CEP orchestration | AWS | 482761 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS SNOW Discovery Review : CI missing Issue Review | Aravindan Renganathan <aravindan.renganathan@assurant.com> | New | 482733 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 4 |  |  | 0 | -4
| Assurant | CEP orchestration | AWS | 482762 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS SNOW Discovery Review : Validate SCP impact for Discovery | Aravindan Renganathan <aravindan.renganathan@assurant.com> | New | 482733 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 3 |  |  | 0 | -3
| Assurant | CEP orchestration | AWS | 484842 | Product Backlog Item | AWS; AWS Platform; Platform Enhancement |  | AWS SNOW Discovery - CI Owner update | Aravindan Renganathan <aravindan.renganathan@assurant.com> | New | 482733 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 |  |  |  | 0 | 0
|  |  |  | 482765 | Product Backlog Item | AWS; AWS Platform; Platform Enhancement |  | VDC Automation Platform implementation : Design Review | Sundaram Diraviam <sundaram.diraviam@assurant.com> | Done | 482735 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 6 | 6 | 0 |  |  |  |  | 80
| Assurant | CEP orchestration | AWS | 482766 | Product Backlog Item | AWS; AWS Platform; Platform Enhancement |  | VDC Automation Platform implementation : Repo review | Sundaram Diraviam <sundaram.diraviam@assurant.com> | New | 482735 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 4 | 0 | 10 | 10 | 6
|  |  |  | 482767 | Product Backlog Item | AWS; AWS Platform; Platform Enhancement |  | VDC Automation Platform implementation : Implementation in Orchestration account | Sundaram Diraviam <sundaram.diraviam@assurant.com> | New | 482735 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 6 | 0 | 12
|  |  |  | 484820 | Product Backlog Item | AWS; AWS Spoke Services; TMO MV Modules |  | Create design document for IAM role requirement for service-to-service communication | Sundaram Diraviam <sundaram.diraviam@assurant.com> | Done | 482735 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 6 | 6 | 0 |  |  |  |  | 80
|  |  |  | 484821 | Product Backlog Item | AWS; Platform Prod Readiness |  | SCP alignment review | Sundaram Diraviam <sundaram.diraviam@assurant.com> | Done | 482736 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 1 | 1 | 0
| Assurant | CEP orchestration | AWS | 484841 | Product Backlog Item | AWS; AWS Platform; Platform Enhancement |  | AWS Account creation factory - Document the features controlled manually | Sundaram Diraviam <sundaram.diraviam@assurant.com> | New | 482736 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 4 | 0 | 0 | 0 | -4
|  |  |  | 482769 | Product Backlog Item | AWS; AWS Platform; Platform Enhancement |  | Dedicated AWS Hub setup : Requirement Followup | Senthil Nathan <senthil.nathan@assurant.com> | Done | 482737 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 4 | 2 | 0 |  |  |  |  | 20
|  |  |  | 482770 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS VPC endpoint provisioning : Automation development and Testing | Senthil Nathan <senthil.nathan@assurant.com> | Done | 482738 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 6
|  |  |  | 482771 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Default Security group automation : Dev and testing | Eric Jackson <eric.jackson1@assurant.com> | Done | 482738 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 6 | 6 | 4
| Assurant | CEP orchestration | AWS | 482772 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS VPC endpoint provisioning implementation | Senthil Nathan <senthil.nathan@assurant.com> | Done | 482738 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 4 |  | 0 | 0 | -4
|  |  |  | 482773 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | Default Security group automation : Implementation | Senthil Nathan <senthil.nathan@assurant.com> | Done | 482738 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 8 | 8 | 0
|  |  |  | 483943 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS VPC Endpoints testcases | Sundaram Diraviam <sundaram.diraviam@assurant.com> | Done | 482738 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 6 | 6 | 0
| Assurant | CEP orchestration | AWS | 482774 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Support Queue : SOP Development | Senthil Nathan <senthil.nathan@assurant.com> | New | 482739 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8 |  |  | 0 | -8
|  |  |  | 482775 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Support Queue : SOP Signoff | Senthil Nathan <senthil.nathan@assurant.com> | New | 482739 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 2 | 5
|  |  |  | 482778 | Product Backlog Item | AWS |  | AWS EFS - Integration testing with EKS | Aravindan Renganathan <aravindan.renganathan@assurant.com> | New | 482740 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 12 | 0 | 12
| Assurant | CEP orchestration | AWS | 482783 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Integration testing : Testcases preparation | Kaliraj Subra Manian <kaliraj.subramanian@assurant.com> | New | 482742 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8 |  |  | 0 | -8
|  |  |  | 482784 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Integration testing : AWS Test account creation | Aravindan Renganathan <aravindan.renganathan@assurant.com> | Done | 482742 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 8 | 8 | 0
|  |  |  | 482785 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Integration Testing : Spoke Provisioning | Kaliraj Subra Manian <kaliraj.subramanian@assurant.com> | Done | 482742 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 8
|  |  |  | 482786 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Integration Testing : TF Code Development | Kaliraj Subra Manian <kaliraj.subramanian@assurant.com> | Done | 482742 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 8
| Assurant | CEP orchestration | AWS | 482787 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Integration Testing : Sample App development | Kaliraj Subra Manian <kaliraj.subramanian@assurant.com> | New | 482742 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 8 |  |  | 0 | -8
|  |  |  | 482788 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Integration Testing : Pipeline implementation | Kaliraj Subra Manian <kaliraj.subramanian@assurant.com> | New | 482742 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8
| Assurant | CEP orchestration | AWS | 482789 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Integration Testing : Spoke Provisioning ; Test cases execution | Kaliraj Subra Manian <kaliraj.subramanian@assurant.com> | New | 482742 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8 |  |  | 0 | -8
|  |  |  | 482790 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Integration Testing : Review and Signoff | Kaliraj Subra Manian <kaliraj.subramanian@assurant.com> | New | 482742 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8
| Assurant | CEP orchestration | AWS | 485532 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Integration Testing : AWS account provisioning, OU creation | Senthil Nathan <senthil.nathan@assurant.com> | New | 482742 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8 |  |  | 0 | -8
|  |  |  | 485533 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Integration Testing : Sandbox environment, SCP development | Senthil Nathan <senthil.nathan@assurant.com> | New | 482742 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8
|  |  |  | 485632 | Product Backlog Item |  |  | Validate NLB Private IP Retrieval for Web Ingress ALB Integration | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 482742 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 3 | 3 | 0
|  |  |  | 483947 | Product Backlog Item | AIZ Labs Modules; AWS; AWS Platform; AWS Spoke Services |  | Infoblox secret management - CFN automation | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | New | 482743 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 12 | 0 | 12
|  |  |  | 485531 | Product Backlog Item | AIZ Labs Modules; AWS; AWS Platform; AWS Spoke Services |  | Infoblox secret management - validation with OU | Senthil Nathan <senthil.nathan@assurant.com> | New | 482743 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 12 | 0 | 12
| Assurant | CEP orchestration | AWS | 480632 | Product Backlog Item | AWS; AWS Platform; AWS Spoke Services; Platform Prod Readiness |  | Update Design diagrams to be simplified | Sundaram Diraviam <sundaram.diraviam@assurant.com> | Done | 482744 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 16 | 16 | 0 | 16 | 0
| Assurant | CEP orchestration | AWS | 484826 | Product Backlog Item | AWS; AWS Platform; AWS Spoke Services; Platform Prod Readiness |  | Update Design diagrams to be simplified | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | New | 482744 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 4 | 0 | 8 | 8 | 4
| Assurant | CEP orchestration | AWS | 484828 | Product Backlog Item |  |  | Design Document update | Aravindan Renganathan <aravindan.renganathan@assurant.com> | Done | 482744 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 8 | 2 | 6 | 8 | 0 |  |  | 80
| Assurant | CEP orchestration | AWS | 483945 | Feature | AWS; AWS Platform; Must Have; Platform Prod Readiness | AWS Platform - JSONAR Implementation |  | Senthil Nathan <senthil.nathan@assurant.com> | In Progress | 481210 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 483946 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Platform JSONAR - EC2 Module Validation | Sundaram Diraviam <sundaram.diraviam@assurant.com> | Done | 483945 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 2 | 2 | 0 | 2 | 0
|  |  |  | 483949 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS RDS MSSQL - Imperva integration validation and Module update palnning | Aravindan Renganathan <aravindan.renganathan@assurant.com> | Done | 483945 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 | 24 | 24 | 24
| Assurant | CEP orchestration | AWS | 484016 | Feature | AWS; AWS Platform; Must Have; Platform Prod Readiness | AWS Root accounts MFA Implementation |  | Senthil Nathan <senthil.nathan@assurant.com> | In Progress | 481210 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-4 |  |  |  | 0 | 0
|  |  |  | 484017 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Root accounts MFA Requirements | Senthil Nathan <senthil.nathan@assurant.com> | Done | 484016 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 4
|  |  |  | 484018 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS Root accounts MFA - Setup coordination | Senthil Nathan <senthil.nathan@assurant.com> | New | 484016 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8
| Assurant | CEP orchestration | AWS | 484838 | Product Backlog Item | AWS; AWS Platform; Platform Enhancement |  | AWS PAR - Review Tenant Groups and Users | Sundaram Diraviam <sundaram.diraviam@assurant.com> | Done | 484837 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 8 | 8 | 0 | 8 | 0
| Assurant | CEP orchestration | AWS | 485776 | Product Backlog Item |  |  | AWS PAR - Tenant groups and Users review | Senthil Nathan <senthil.nathan@assurant.com> | Done | 484837 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 10 | 10 | 0 | 10 | 0
| Assurant | CEP orchestration | AWS | 485658 | Feature | AWS; AWS Spoke Services | AWS Budget and Cost Alerts |  | Aravindan Renganathan <aravindan.renganathan@assurant.com> | New | 481210 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 |  |  |  | 0 | 0
|  |  |  | 485765 | Product Backlog Item | AWS; AWS Spoke Services; Platform Prod Readiness |  | AWS NLB 0.85: Coding | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 485860 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 4 | 3 | 0
| Assurant | CEP orchestration | AWS | 485863 | Product Backlog Item | AWS; AWS Spoke Services; Platform Prod Readiness |  | AWS NLB 0.85: Testing | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 485860 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 3 | 3 | 0 | 3 | 0
| Assurant | CEP orchestration | AWS | 485864 | Product Backlog Item | AWS; AWS Spoke Services; Platform Prod Readiness |  | AWS NLB 0.85: Incorporate PR Review Comments | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | In Progress | 485860 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 8 |  | 8 | 8 | 0
|  |  |  | 485400 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS ALB 0.80: Coding | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 485862 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 8 |  | 0
|  |  |  | 485401 | Product Backlog Item | AWS; AWS Platform; Platform Prod Readiness |  | AWS ALB 0.80: Testing | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 485862 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-5 | 3 |  | 3
|  |  |  | 485466 | Product Backlog Item | AWS; AWS Spoke Services; Platform Prod Readiness |  | AWS ALB 0.80: Incorporate PR Review Comments | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | In Progress | 485862 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-6 | 6 |  | 0
| Assurant | CEP orchestration | AWS | 482743 | Feature | AIZ Labs Modules | AWS Secrets management for Infoblox and Datadog |  | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | New | 481210 | GT.ICS-Cloud Planning\2025\2025 Q1 |  |  |  | 0 | 0
| Assurant | CEP orchestration | AWS | 482779 | Product Backlog Item | AIZ Labs Modules |  | AWS Secrets management for Infoblox and Datadog - Design review | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 482743 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-3 | 5 | 3 | 0 | 3 | -2
| Assurant | CEP orchestration | AWS | 482780 | Product Backlog Item | AIZ Labs Modules |  | AWS Secrets management for Infoblox and Datadog : Implementation | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 482743 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-3 | 8 | 8 | 0 | 8 | 0
| Assurant | CEP orchestration | AWS | 482781 | Product Backlog Item | AIZ Labs Modules |  | AWS Secrets management for Infoblox and Datadog - Testing | Yogesh Selvarajan <yogesh.selvarajan@assurant.com> | Done | 482743 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-3 | 8 | 8 | 0 | 8 | 0
|  |  |  | 482744 | Feature | Platform Prod Readiness | AWS Spoke services Design Document update |  | Senthil Nathan <senthil.nathan@assurant.com> | New | 481210 | GT.ICS-Cloud Planning\2025\2025 Q1
|  |  |  | 482502 | Product Backlog Item | Platform Prod Readiness |  | AWS Platform Production readiness checklist | Senthil Nathan <senthil.nathan@assurant.com> | Done | 482744 | GT.ICS-Cloud Planning\2025\2025 Q1\2025 Q1 Sprint-3 | 12 | 12 | 0
|  |  |  | 483331 | Feature | Platform Prod Readiness | AWS - Quarterly Review of Design documents |  | Senthil Nathan <senthil.nathan@assurant.com> | New | 481210 | GT.ICS-Cloud Planning\2025